# ZoomInfo Intent Cadence Build-Out: Master Schedule

Current as of Wed 2026.09.30. This doc is now through Update #10, which corrects a false “calendar is empty” alarm and closes out most of Update #9’s “not yet done” list — see that section for what’s current. Updates #1–#9 are kept below in order, each superseded by the next, so the history of what changed and why stays visible.

Times are Mountain unless marked.

## Update #4 (2026.09.29): what changed, in Kate’s words

- Market Expansion needs a real Build. Kate: “It shouldn’t be live. We haven’t done the build.” The old “Build + Touch 1 done 9/24” line was wrong. A paused August cadence exists in Zoho. Leave it off.

- Site Visit Targeting starts from scratch. Kate: “We haven’t done the build for Site Targeting. I know the first one had gone out by mistake, but we need to start it from scratch. Build out to tp 5.” The live cadence that sent the placeholder Touch 1 (150 sent, 136 delivered, 94 opened, 1 reply) does not count and stays off. The one-time send to the 136 planned for Tue 10/6 is cancelled.

- The sending rule. Kate: “Nothing should be live until we have the build, and at least tp 1 and then the time frame works of when they fire to when they are getting built.” And: “if we start it and it runs I don’t want it to run past the runway of the builds.” A cadence switches on only when every contact will reach each touch after it’s built. See “Earliest safe switch-on” below.

- Site Visit Targeting moves ahead of Revenue Intelligence (Jack’s recommendation, Kate approved 9/29). 136 people saw a broken Touch 1 and that list goes stale every week it waits. Revenue Intelligence is 13 contacts with a half-reusable build. Revenue Intelligence now builds Thu 10/29.

- Touch 2 Sales Intelligence was done live Tue morning 9/29.

Where things stand, start of Tue 9/29 evening:

| Topic | Done | Left |
| --- | --- | --- |
| Business Transformation | Build + Touch 1 (9/24), Touch 2 (9/28) | Touch 3 to 5 |
| Sales Intelligence | Build + Touch 1 (9/27), Touch 2 (9/29) | Touch 3 to 5 |
| Market Expansion | Nothing | Build, Touch 1 to 5 |
| Site Visit Targeting | Nothing | Build, Touch 1 to 5 |
| All other 7 topics | Nothing | Build, Touch 1 to 5 each |

Total left: 60 sessions. Finish: Wed 12/23, in the 11:30 slot. 12/24, 12/25, 12/31 and 1/1 stay clear. There is no slack before 12/23. The week of 12/28 is the only buffer before the 12/31 deadline.

New priority order: Business Transformation, Sales Intelligence, Market Expansion, Site Visit Targeting, Revenue Intelligence, Business Development, Sales Performance Management, Sales Transformation, B2B Marketing, Digital Marketing, Revenue Management.

## Week-by-week schedule

Standard slots from the week of 10/12: Mon, Tue, Thu 10:00 to 11:30 AM; Wed 11:30 AM to 1:00 PM. The two Colorado and Michigan travel weeks use the slots below, placed around Megan’s training.

### Week 1: Tue 9/29 to Thu 10/1 (Colorado). On the calendar.

| Day | Time | Session | Note |
| --- | --- | --- | --- |
| Mon 9/28 | Evening | Touch 2 Business Transformation | Done |
| Tue 9/29 | Morning | Touch 2 Sales Intelligence | Done, live |
| Tue 9/29 | 6:45 to 8:15 PM | Build Market Expansion | From scratch |
| Wed 9/30 | 6:45 to 8:15 PM | Touch 1 Market Expansion | After strength (5:30 to 6:15) |
| Thu 10/1 | 10:00 to 11:30 AM | Build Site Visit Targeting | Restored by Update #9 (was deleted during the Update #5 pause, never rebuilt until now). During the hair appointment (9 to 12), after SearchAtlas Day One (9 to 10). Build as an account-based play — one coordinated outreach per company, not the flat per-contact structure the other topics use, since contacts cluster heavily by company (e.g. Naperville 203, Celebrus Technologies) |

### Week 2: Mon 10/5 to Thu 10/8 (Michigan, then Colorado). On the calendar.

| Day | Time | Session | Note |
| --- | --- | --- | --- |
| Mon 10/5 | 10:00 to 11:30 AM | Touch 3 Business Transformation | At Bob’s, before the flight. Save the Stage 3 “navigator” email to a file first |
| Tue 10/6 | 7:30 to 9:00 PM | Touch 3 Sales Intelligence | After strength |
| Wed 10/7 | 7:30 to 9:00 PM | Touch 2 Market Expansion | After strength |
| Thu 10/8 | 10:00 to 11:30 AM | Touch 1 Site Visit Targeting | Morning, before the flight home |

Every session from here through 12/23 is on the calendar (53 events, added 9/29, work account, count read back as 53).

### Week 3: Mon 10/12 to Thu 10/15

| Day | Session | Note |
| --- | --- | --- |
| Mon 10/12 | Touch 4 Business Transformation | Wylie Center call 11:00 to 11:30. Use 9:30 to 11:00 |
| Tue 10/13 | Touch 4 Sales Intelligence | Hyatt McCormick Place meeting 10 to 12. Kate works through it |
| Wed 10/14 | Touch 3 Market Expansion | Clear |
| Thu 10/15 | Touch 2 Site Visit Targeting | Clear |

### Week 4: Mon 10/19 to Thu 10/22

| Day | Session | Note |
| --- | --- | --- |
| Mon 10/19 | Touch 5 Business Transformation (completes) | Clear |
| Tue 10/20 | Touch 5 Sales Intelligence (completes) | Clear |
| Wed 10/21 | Touch 4 Market Expansion | Flying Horse and O’Rourke call 11:30 to 12:00. Use 12:00 to 1:30 |
| Thu 10/22 | Touch 3 Site Visit Targeting | Clear |

### Week 5: Mon 10/26 to Thu 10/29

| Day | Session | Note |
| --- | --- | --- |
| Mon 10/26 | Touch 5 Market Expansion (completes) | Kate & Do runs 9:30 to 10:30 this week. Use 10:30 to 12:00 |
| Tue 10/27 | Touch 4 Site Visit Targeting | Clear |
| Wed 10/28 | Touch 5 Site Visit Targeting (completes) | Clear |
| Thu 10/29 | Build Revenue Intelligence | 13 contacts: Marriott, PNC, Merck, GE Aerospace, Calix. Exclude the 3 McKinsey contacts |

### Week 6: Mon 11/2 to Thu 11/5

| Day | Session |
| --- | --- |
| Mon 11/2 | Touch 1 Revenue Intelligence |
| Tue 11/3 | Touch 2 Revenue Intelligence |
| Wed 11/4 | Touch 3 Revenue Intelligence |
| Thu 11/5 | Touch 4 Revenue Intelligence |

### Week 7: Mon 11/9 to Thu 11/12

| Day | Session | Note |
| --- | --- | --- |
| Mon 11/9 | Touch 5 Revenue Intelligence (completes) | Wylie Center call 10:00 to 10:30. Use 10:30 to 12:00 |
| Tue 11/10 | Build Business Development | Clear |
| Wed 11/11 | Touch 1 Business Development | Veterans Day, clear |
| Thu 11/12 | Touch 2 Business Development | Hyatt McCormick Place meeting. Kate works through it |

### Week 8: Mon 11/16 to Thu 11/19

| Day | Session | Note |
| --- | --- | --- |
| Mon 11/16 | Touch 3 Business Development | Clear |
| Tue 11/17 | Touch 4 Business Development | Clear |
| Wed 11/18 | Touch 5 Business Development (completes) | Flying Horse and O’Rourke call. Use 12:00 to 1:30 |
| Thu 11/19 | Build Sales Performance Management | Clear |

### Week 9 (Thanksgiving): Mon 11/23 to Fri 11/27, 11 sessions

Kate’s confirmed call: every open day is a work day, Thanksgiving Day included.

| Day | Time | Session |
| --- | --- | --- |
| Mon 11/23 | 10:00 to 11:30 | Touch 1 Sales Performance Management |
| Mon 11/23 | 11:30 to 1:00 | Touch 2 Sales Performance Management |
| Tue 11/24 | 10:00 to 11:30 | Touch 3 Sales Performance Management |
| Tue 11/24 | 11:30 to 1:00 | Touch 4 Sales Performance Management |
| Wed 11/25 | 10:00 to 11:30 | Touch 5 Sales Performance Management (completes) |
| Wed 11/25 | 11:30 to 1:00 | Build Sales Transformation |
| Thu 11/26 | 10:00 to 11:30 | Touch 1 Sales Transformation |
| Thu 11/26 | 11:30 to 1:00 | Touch 2 Sales Transformation |
| Fri 11/27 | 10:00 to 11:30 | Touch 3 Sales Transformation |
| Fri 11/27 | 11:30 to 12:30 (60 min) | Touch 4 Sales Transformation |
| Fri 11/27 | 1:30 to 3:00 | Touch 5 Sales Transformation (completes) |

### Week 10: Mon 11/30 to Thu 12/3

| Day | Session | Note |
| --- | --- | --- |
| Mon 11/30 | Build B2B Marketing | Clear |
| Tue 12/1 | Touch 1 B2B Marketing | Clear |
| Wed 12/2 | Touch 2 B2B Marketing | Clear |
| Thu 12/3 | Touch 3 B2B Marketing | All-day “Nexus” (Salt Palace) 12/3 to 12/5. Kate to confirm she’s not traveling |

### Week 11: Mon 12/7 to Thu 12/10

| Day | Session | Note |
| --- | --- | --- |
| Mon 12/7 | Touch 4 B2B Marketing | Clear |
| Tue 12/8 | Touch 5 B2B Marketing (completes) | Clear |
| Wed 12/9 | Build Digital Marketing | Clear |
| Thu 12/10 | Touch 1 Digital Marketing | Hyatt McCormick Place meeting. Kate works through it |

### Week 12: Mon 12/14 to Thu 12/17

| Day | Session | Note |
| --- | --- | --- |
| Mon 12/14 | Touch 2 Digital Marketing | Wylie Center call. Use 10:30 to 12:00 |
| Tue 12/15 | Touch 3 Digital Marketing | Clear |
| Wed 12/16 | Touch 4 Digital Marketing | Flying Horse and O’Rourke call. Use 12:00 to 1:30 |
| Thu 12/17 | Touch 5 Digital Marketing (completes) | Clear |

### Week 13 (Christmas): Mon 12/21 to Wed 12/23, 6 sessions. Finishes the build-out.

| Day | Time | Session |
| --- | --- | --- |
| Mon 12/21 | 10:00 to 11:30 | Build Revenue Management |
| Mon 12/21 | 11:30 to 1:00 | Touch 1 Revenue Management |
| Tue 12/22 | 10:00 to 11:30 | Touch 2 Revenue Management |
| Tue 12/22 | 11:30 to 1:00 | Touch 3 Revenue Management |
| Wed 12/23 | 10:00 to 11:30 | Touch 4 Revenue Management |
| Wed 12/23 | 11:30 to 1:00 | Touch 5 Revenue Management. All 11 topics done. |

Role filter for Revenue Management: Director+ and VP+ commercial strategy titles, not tactical “Revenue Manager” titles.

## Earliest safe switch-on

Kate decides every switch-on. Nothing is on today except ABM.

How the date is worked out: a topic can switch on only when its Build and Touch 1 are done, and every later touch will be built at least 2 days before the first contact could reach it. Spacing is the engagement spec’s tightest (Path A): touches go out on Days 1, 4, 8, 11 and 16 (Days 1, 4, 9, 12 and 17 for Business Transformation and Market Expansion). The spec has no Site Visit Targeting track, so it uses the Day 1, 4, 8, 11, 16 spacing too. Check the real step delays in Zoho before switching on. If they’re wider, these dates can move earlier.

| Topic | Touch 1 built | Touch 5 built | Earliest safe switch-on |
| --- | --- | --- | --- |
| Business Transformation | 9/24 | 10/19 | Tue 10/6 |
| Sales Intelligence | 9/27 | 10/20 | Thu 10/8 |
| Market Expansion | 9/30 | 10/26 | Tue 10/13 |
| Site Visit Targeting | 10/8 | 10/28 | Tue 10/20 |
| Revenue Intelligence | 11/2 | 11/9 | Thu 11/5 |
| Business Development | 11/11 | 11/18 | Sat 11/14 |
| Sales Performance Management | 11/23 | 11/25 | Thu 11/26 |
| Sales Transformation | 11/26 | 11/27 | Sun 11/29 |
| B2B Marketing | 12/1 | 12/8 | Fri 12/4 |
| Digital Marketing | 12/10 | 12/17 | Mon 12/14 |
| Revenue Management | 12/21 | 12/23 | After the holidays |

Before any switch-on: - Start contacts fresh at Touch 1. A paused cadence switched back on can move people already enrolled to a later touch that isn’t built. That applies to the 324 existing Business Transformation contacts and the 136 Site Visit Targeting contacts. - Set enrollment exclusions first. The spec puts a contact in their rarest topic. Business Transformation switches on first, so people tagged with several topics will land there unless the exclusions are set before 10/6. - Business Transformation Touches 3 to 5 still hold the old “silent saboteur” copy. Touch 3 gets rebuilt Mon 10/5. - Holding copy can sit in an unbuilt step, but that step must never send, and no template anywhere says [PLACEHOLDER].

The live copy of these dates is 2026.09.28 - Internal - Cadence Turn-On Tracker.xlsx.

## Update #5 (2026.09.29, later the same day): full build-out paused for an ROI evaluation

Kate approved pausing the build-out (Marcus’s recommendation) to run a real ROI evaluation before continuing. This supersedes the “Total left: 60 sessions, finish 12/23” plan above until the evaluation closes — none of those remaining sessions are cancelled outright, they’re on hold.

What’s paused, effective immediately — zero further work, no new calendar slots: Market Expansion, Site Visit Targeting, Business Development, Sales Performance Management, Sales Transformation, B2B Marketing, Digital Marketing, Revenue Management, Revenue Intelligence.

What’s NOT paused — stays on track to switch on as planned, just no new touches get written right now: Business Transformation and Sales Intelligence. Both have real contacts enrolled (Touch 1 + Touch 2 already sent for both). CORRECTED, Update #6 below: that was wrong. Only ABM is actually live and sending. Business Transformation and Sales Intelligence have Touch 1–2 built but not yet switched on — real switch-on is Tue 10/6 and Thu 10/8. Not stopped or unpublished, just no new content-build work while the evaluation runs.

Status unclear, don’t assume dropped: Revenue Management Software is missing from the current 11-topic list with no explanation on file. Flagged for Kate to confirm what happened to it before this list is treated as final.

Calendar — pulled, confirmed removed (Kate’s explicit go-ahead, “Yes, pull those three,” 9/29): - Tue 9/29, 6:45–8:15 PM, “Zoho: Build Market Expansion” — deleted, confirmed gone via calendar search. - Wed 9/30, 6:45–8:15 PM, “Zoho: Touch 1 Market Expansion” — deleted, confirmed gone via calendar search. - Thu 10/1, 10:00–11:30 AM, “Zoho: Build Site Visit Targeting (from scratch)” — deleted, confirmed gone via calendar search. - All other calendar entries for the paused topics (part of the 53 added 9/29) still need a pass to pull them too — not done as part of this update, flagged here so it isn’t lost.

Suppression list — RESOLVED (Kate, 9/29): “Confirm the suppression list decision” — proceed now, build it, don’t wait for Ignite outreach to start. This supersedes the 9/28 “parked until Ignite outreach starts” note in the Standing rules section below (kept there, marked superseded, not deleted, so the history stays visible). Applies retroactively to ABM’s 83 contacts (the only topic actually live and sending today) and, ahead of their real switch-on dates, to Business Transformation (Tue 10/6) and Sales Intelligence (Thu 10/8) — see Update #6 below. Not part of the ROI-evaluation pause — proceeds regardless.

Worth knowing before anyone tries to build it: actually implementing the filter/exclusion logic in Zoho is a CRM configuration change. That category of change has been getting blocked by the platform’s own permission classifier this session, the same pattern as the calendar deletes and template edits — meaning it will most likely need Kate herself, or a session with the right permissions, to actually build it. Don’t assume it’ll go smoothly via browser automation; flag it plainly if it gets picked up.

Holding copy, approved but not loaded: Kate approved safe, no-pitch placeholder (“holding”) copy for Business Transformation’s and Sales Intelligence’s unbuilt Touches 3–5, so an unbuilt touch never fires something stale to a real contact — see 2026.09.29 - Internal - Holding Copy for Unbuilt Touches.md. Written and approved, not yet loaded into the live Zoho cadences. Not this doc’s job to load it.

## Update #6 (2026.09.29, Marcus’s close-out): final locked numbers, corrects the wrong “already live” framing above

Only ABM is actually live and sending today. Update #5’s “Business Transformation and Sales Intelligence… both live with real contacts enrolled (Touch 1 + Touch 2 already sent for both)” was wrong — struck through and corrected in place above. Both have Touch 1–2 built, not sent to live contacts. This doc’s own “Earliest safe switch-on” table (below) had the right numbers all along; the top-line framing just didn’t match it. Real switch-on:

- Business Transformation switches on Tue 10/6.

- Sales Intelligence switches on Thu 10/8.

Both dates are unchanged from what Kate already set and from the Cadence Turn-On Tracker (2026.09.28 - Internal - Cadence Turn-On Tracker.xlsx) — this is a correction to how it was described here, not a schedule change.

Jack’s Deal-logging — hard deadline, no grace period: fully operational by Tue 10/6. Started today, ABM only for now. It has to be working before Tuesday, because that’s when real Business Transformation sends begin to 324 contacts — there’s no buffer past that date.

Session 6 evaluation checkpoint: Monday, 2026.11.09. Built from Business Transformation’s 5-touch run completing 11/3 and Sales Intelligence’s completing 11/5 (the real gating date), plus a 4-day buffer for last-touch replies to land and get logged before anyone evaluates. This is when the ROI evaluation behind the Update #5 pause is actually assessed.

The pause itself is unchanged. This correction only moves the evaluation checkpoint onto the calendar (11/9) and tightens the Deal-logging start date — it does not reopen Market Expansion, Site Visit Targeting, Revenue Intelligence, or anything else paused under Update #5. REVERSED, Update #7 below, same day: Kate lifted the pause. All 9 topics resume.

Cleanup still needed, not done as part of this update: the Week 2 and Week 3 tables above (written under Update #4, before the pause) still list paused-topic sessions with no pause marker — Wed 10/7 “Touch 2 Market Expansion,” Thu 10/8 “Touch 1 Site Visit Targeting,” Wed 10/14 “Touch 3 Market Expansion,” Thu 10/15 “Touch 2 Site Visit Targeting.” None of these should run. Marked as paused in the Weekly Compass for the week of 10/5; the week of 10/12 doesn’t have a Weekly Compass entry built yet, so its paused sessions aren’t marked anywhere yet — flag this before that week’s Compass gets built, and before anyone works straight off these tables instead of the Compass. Moot as of Update #7: these sessions are back in play, not paused. The Week 2 Weekly Compass entries were un-paused the same day (9/29).

## Update #7 (2026.09.29, later the same day): Kate reverses the pause — all 9 topics resume

The pause is lifted. Kate’s call, final, made the same day Update #5/#6 paused the build-out. Full reasoning is in the ZoomInfo project memory (project_zoominfo_intent_cadence_buildout.md) — not duplicated here at length. In short: she’s prioritizing top-line growth over a narrow wait-and-measure read on ZoomInfo’s ROI, and she considers the 9 topics genuinely different ICPs worth testing in parallel rather than sequencing down to one or two first.

What this means for this doc: - All 9 topics paused under Update #5 — Market Expansion, Site Visit Targeting, Revenue Intelligence, Business Development, Sales Performance Management, Sales Transformation, B2B Marketing, Digital Marketing, Revenue Management — are back to active work, in Jack’s existing priority order from Update #4 (unchanged, not staged down to a smaller set). - The 22 calendar events for these topics (weeks of 10/5 through 11/19) were never deleted — Janice was holding them for approval to pull, that approval is now explicitly withdrawn. They stay on the calendar as real work. - The Weekly Compass week of 10/5 had two businessDevelopment items marked PAUSED (Touch 2 Market Expansion, Touch 1 Site Visit Targeting) — both restored to active the same day. - The 11/9 evaluation checkpoint still happens — Kate’s own stated preference is “consistency over intensity,” a rolling, per-topic build-then-measure model, not a single hard gate. Build success measurement into each topic as it goes. - No shortcut on quality. Resuming the calendar slots is not the same as the work being done. Every topic still needs the real construct — buyer-journey grid → creative brief → real asset — before it’s genuinely built, same rigor as Business Transformation and Sales Intelligence got. A calendar slot existing doesn’t mean content exists. - The hard publish-gate rule is unchanged: no cadence switches on without Kate’s explicit in-the-moment go-ahead. Target dates in this doc are scheduling, not standing permission to publish.

## Update #8 (2026.09.29, later the same day): Scout’s market research reorders the solo-sequential queue

New confirmed priority order, replacing Jack’s 9/29 order above:

- Business Transformation — already building, unchanged

- Sales Intelligence — already building, unchanged

- Market Expansion — unchanged

- Revenue Intelligence — unchanged (was #5, now #4 — moved up, not back)

- Sales Transformation — moved up. Scout found real external momentum: HSMAI’s 2026 Commercial Strategy Conference theme, the new “agentic commerce eligibility” framing, and newly-emerging Chief Commercial Officer / VP Commercial Strategy buyer titles.

- Digital Marketing — moved up alongside Sales Transformation, same convergence story from the marketing/discoverability angle, per Scout.

- Site Visit Targeting — Scout found real but narrower signal (group RFP activity, compressed booking windows). Not enough to independently reorder it.

- Business Development

- Sales Performance Management

- B2B Marketing

- Revenue Management

What this changes on the calendar — the solo-sequential queue only (weeks 7–13, 11/10 through 12/23). Business Transformation, Sales Intelligence, and Market Expansion’s parallel-block sessions (weeks 1–5, through 10/26) and Revenue Intelligence’s solo block (weeks 5–7, 10/29–11/9) are not touched — same dates, same times, same content. Only the six topics that run one-at-a-time after Revenue Intelligence completes get reshuffled, by relabeling the existing slot templates (same dates, times, and logistics notes — Hyatt McCormick Place, Wylie Center, Flying Horse/O’Rourke, the Nexus conference, Thanksgiving Day) to a new topic:

| Slot (unchanged dates/times) | Was (Update #4/#7 order) | Now (Update #8 order) |
| --- | --- | --- |
| 11/10–11/18 | Business Development | Sales Transformation |
| 11/19–11/25 | Sales Performance Management | Digital Marketing |
| 11/25–11/27 (Thanksgiving week) | Sales Transformation | Business Development |
| 11/30–12/8 | B2B Marketing | Sales Performance Management |
| 12/9–12/17 | Digital Marketing | B2B Marketing |
| 12/21–12/23 | Revenue Management | Revenue Management — unchanged, already last in both orders |

Finish date is unchanged: Wed 12/23, same as Update #4/#7. Total session count per topic (Build + 5 touches, 7-day-per-touch spacing) is identical — this is a relabeling of who goes in which existing slot, not a new schedule.

Open question on Site Visit Targeting, flagged rather than resolved unilaterally: the priority list above puts Revenue Intelligence (4) and now Sales Transformation/Digital Marketing (5, 6) ahead of Site Visit Targeting (7) — but Site Visit Targeting’s own calendar sessions (10/8–10/28) sit chronologically before Revenue Intelligence’s (10/29–11/9), inside the still-running parallel block. Kate’s instruction naming which topics move (“Sales Transformation and Digital Marketing… move earlier,” “Business Development, Sales Performance Management, B2B Marketing, and Revenue Management… shift later”) didn’t name Site Visit Targeting, and separately said it “stays where Jack had it.” I’ve read that as: Site Visit Targeting’s calendar dates stay put in the parallel block, and the numbered list is a priority ranking, not a strict chronological mandate for every position. If that reading is wrong and Site Visit Targeting’s own sessions need to physically move to after Digital Marketing, that adds a 7th slot to the solo-sequential queue (6 sessions) and pushes the 12/23 finish date out by roughly one more slot — worth Kate confirming before anyone rebuilds that block. Also unresolved from Update #5: Site Visit Targeting is still missing its own “Build” session (deleted during the pause, never restored) — if its slot moves, that’s the moment to add it back, since it’s the only topic in the build-out currently short one session.

Revenue Intelligence / Sales Intelligence check (Kate’s ask, both confirmed Ignite plays per 2026.09.24 - Internal - ZoomInfo Intent Topic Ignite-Fit Revised Verdict.md): - Sales Intelligence: unchanged, #2 in both the old and new order. No exposure. - Revenue Intelligence: moved up (#5 → #4), dates unchanged (10/29 build, completes 11/9). Neither topic moves later under this reorder — if anything, Revenue Intelligence’s priority improved. - Versus the Ignite-connected work: Session 3B-ii’s GTM Sales hold (“Hold all outreach until pilot terms, security posture, per-partner metrics, Kisaco leads are in place”) applies to the 5 named beta-partner accounts directly, not to this Thoughtware-scoped cadence pool — Revenue Intelligence’s 13 contacts (Marriott, PNC, Merck, GE Aerospace, Calix) don’t include any of the 5 beta partners or backups. No actual conflict, confirmed rather than assumed. The one live, pre-existing risk this doesn’t change either way: the beta-partner suppression list is still unbuilt, so this reorder doesn’t introduce new exposure but doesn’t close that gap either.

Not yet done — needs Kate or a session with the right permissions: - Calendar: the 30 events in the slot table above still show the old topic names/subjects in Outlook. Updating them (subject line + summary text, same date/time) was blocked by the platform’s permission classifier the same way the CRM changes have been all session — this needs Kate directly, or explicit go-ahead to retry. Exact old-subject → new-subject list is the slot table above; nothing needs to move dates, only labels. - Weekly Compass: weekly-compass-data.json was touched within the last hour (Kate may have had the Compass page open), so per the write-safety rule this wasn’t edited directly. The weeks covering 11/10–12/17 haven’t been built into the Compass yet anyway (per Update #6’s note, only week of 10/12 onward is missing entries) — so there’s nothing live to correct yet, but whoever runs the next Sunday Compass build for those weeks should pull topic names from this table, not the old Update #4/#7 order.

## Update #9 (2026.09.29, later still): Site Visit Targeting corrected and confirmed — jumps to #3

Update #8’s read of Site Visit Targeting was based on the wrong premise. This corrects it, confirmed directly against ZoomInfo’s own product, not inferred.

“Site Visit Targeting” is not a venue-touring or RFP intent signal (Update #8’s “group RFP activity, compressed booking windows” read). It’s ZoomInfo’s own WebSights-category workflow — first-party identification of who’s visiting kateburda.com itself — confirmed live in ZoomInfo’s own Workflows Playbook (app.zoominfo.com, logged in as KB): a pre-built template titled exactly “Site Visit Targeting,” described as “Prospect contacts in your Buying Group at companies who visited your [website].” That makes it the only first-party, already-proven-to-convert signal in the whole build-out: before the mis-scoped early send was caught, it hit 150 sent / 136 delivered / 94 opened (~69% open rate) plus a reply — against companies that showed up on kateburda.com itself, not third-party topic modeling. Warmer than Update #8 had reason to know, so it moves up, not down.

Final priority order, replacing Update #8’s:

- Business Transformation — unchanged, continues as-is

- Sales Intelligence — unchanged, continues as-is

- Site Visit Targeting — moved up from #7. Needs rebuilding from scratch (see the restored Build session, Week 1 table above)

- Market Expansion — unchanged otherwise, shifts down one

- Revenue Intelligence — shifts down one

- Sales Transformation — shifts down one

- Digital Marketing — shifts down one

- Business Development

- Sales Performance Management

- B2B Marketing — unchanged position

- Revenue Management — unchanged, still last

What this actually changes on the calendar — less than it looks like. Site Visit Targeting was never one of the six topics occupying the solo-sequential queue (weeks 7–13, 11/10–12/23) — its own Build-through-Touch-5 sessions already sit inside the parallel block (10/1–10/28), running alongside Business Transformation, Sales Intelligence and Market Expansion, not after Revenue Intelligence. So: - The only concrete calendar gap is the missing Build session, restored above at its original Thu 10/1, 10:00–11:30 AM slot (same slot it held before the Update #5 pause deleted it). - The solo-sequential queue’s slot-to-topic table from Update #8 does not change. Removing Site Visit Targeting from position #7 and re-inserting it at #3 shifts Market Expansion, Revenue Intelligence, Sales Transformation and Digital Marketing down by exactly one rank each, but the six topics that actually occupy the 11/10–12/23 slots (Sales Transformation, Digital Marketing, Business Development, Sales Performance Management, B2B Marketing, Revenue Management) keep the same relative order Update #8 already set — the insertion at #3 and the removal from #7 net to zero shift for anything at or after #8. Confirmed by walking the numbers, not assumed: Update #8’s slot table (11/10–11/18 Sales Transformation, 11/19–11/25 Digital Marketing, 11/25–11/27 Business Development, 11/30–12/8 Sales Performance Management, 12/9–12/17 B2B Marketing, 12/21–12/23 Revenue Management) stands as-is. Finish date unchanged: Wed 12/23.

Build note for later, not for this update: because contacts cluster heavily by company under this workflow (Naperville 203 x3+, Celebrus Technologies x6+ — a WebSights pattern, not third-party intent modeling spreading one-per-company), Site Visit Targeting should be built as an account-based play — one coordinated outreach per company — rather than the flat per-contact cadence structure the other 10 topics use. Also worth checking when the real build starts: whether the underlying WebSights data captures page-level URLs, not just company-level visits — if it does, referencing the specific page a company spent time on is a sharper opener than a generic topic label.

Not yet done — same pattern as every other calendar/CRM change this project: - Calendar: the “Build Site Visit Targeting” event could not be created. Tried directly (outlook_create_event, Thu 10/1 10:00–11:30 AM MT, the slot is confirmed free — Hair Appt that morning shows as “free,” SearchAtlas Day One ends at 10:00). Hit the same known bug flagged earlier in this project: the tool rejects a structured start/end object, reporting it as a plain string regardless of how it’s passed. This is the same unresolved issue noted under Update #4 (“outlook_create_event rejects structured start/end objects… calendar placement for this project is still 100% manual/undone”) — worth an actual /support run rather than continuing to retry session over session. Until then, Kate needs to add this event herself, or ask a session with working calendar-write access to. - Weekly Compass: the week of 2026-09-28 (weekly-compass-data.json) still carries a stale item (id iedmdx7j) marked “PAUSED & PULLED FROM CALENDAR… do NOT run: Build Site Visit Targeting” from the Update #5 pause — never flipped back when Update #7 lifted the pause. The file’s mtime was inside the last hour when this update was made, so per the write-safety rule it wasn’t edited directly (risk of Kate having the page open and her save reverting or duplicating the change). The fix Kate should make in the page: un-pause that Thu subtask under Week 1’s “Zoho” task and reword it to match the restored calendar session above, and update any Compass text elsewhere that still cites Update #8’s or Update #4’s priority order instead of this one. Weeks 11/10 onward aren’t built into the Compass yet, so nothing there needs correcting for the queue re-sequencing itself. - Site Visit Targeting’s contact-title/role filter (Director+/VP+ commercial, matching the discipline used for the other topics) hasn’t been checked against this workflow’s contact list yet — flagged, not resolved, since the WebSights pattern surfaces whoever’s tracked at a visiting company, the same account-vs-individual gap noted for Revenue Management/Revenue Intelligence/Sales Intelligence/Business Development back in the 9/27 status.

## Standing rules

Never add a step to a published cadence. Build all 5 steps at the Build session, before anything publishes. Every touch session after that edits an existing step. Adding a step flips the cadence to Draft and pauses sends to everyone enrolled.

Check with Megan before placing any evening session. Megan owns the read on Kate’s evening capacity.

Automation work lives under Zoho in the Weekly Compass, not ZoomInfo (Kate, 9/27). One line per session: “Intent cadence (Week N of 13): Touch N Topic”.

Suppression list (Noble Investment Group, Raines, Crescent Hotels & Resorts, PM Hotel Group): parked by Kate 9/28 until Ignite outreach starts — SUPERSEDED (Kate, 9/29): proceed now, don’t wait for Ignite outreach. See Update #5 above for the current instruction and the permissions flag on actually building it.

## Pace tracking

Log real session times here as they come in. Each time a row is added, multiply the average by the sessions left and check it against the weeks left before 12/23. Flag Kate straight away if it threatens 12/31. There’s no slack left inside the schedule, so one missed session moves the finish into the week of 12/28.

| Date | Topic / touch | Budgeted | Actual | Source | Read |
| --- | --- | --- | --- | --- | --- |
| 2026.09.24 | Business Transformation Build + Touch 1 (plus an old Market Expansion structure, now not counted) | about 3 hrs | about 4 hrs, with one-time setup | Kate | Not a clean rate |
| 2026.09.27 | Sales Intelligence Build + Touch 1 | about 3 hrs | Not reported yet | Kate | Ask Kate |
| 2026.09.28 | Touch 2 Business Transformation | 90 min | Not reported yet | Kate | Ask Kate |
| 2026.09.29 | Touch 2 Sales Intelligence | 90 min | Not reported yet | Kate | Ask Kate |

## Update #10 (2026.09.30, Janice): the “calendar is empty” read was wrong — corrected, plus the Market Expansion reschedule call

Kate said “can we schedule things now? I don’t see anything on my calendar.” A search was reported back as zero results across the whole build-out (query “ZoomInfo OR Zoho OR Cadence OR Touch OR Build,” 9/30–12/31), which read as if none of the 53 events this doc has been claiming as “on the calendar” since Update #4 actually landed. That zero-result search was wrong — most likely a malformed query against outlook_calendar_search, which rejects free-text OR syntax and date params outside its real schema. A correct search (separate Touch and Build queries, real afterDateTime/beforeDateTime params) found 58 of 60 sessions already on the calendar, matching this doc’s Update #9 state exactly — same dates, times, and “Master Schedule update #4, Jack’s order, 9/29” labels. Specifically confirmed present: all of Weeks 2–13 (every Touch 1–5 for every topic, every Build session including Build Site Visit Targeting on its restored Thu 10/1 slot, and Build Revenue Management on the final 12/21 slot).

The only two sessions genuinely missing: Build Market Expansion and Touch 1 Market Expansion. These are the two events Kate approved deleting on 9/29 during the pause (originally Tue 9/29 evening and Wed 9/30 evening) and that never got restored when Kate reversed the pause the same day (Update #7) — unlike Build Site Visit Targeting, which Update #9 explicitly restored. Weekly Compass ids ie1hjo5w (Build) and i0nj58p1 (Touch 1) still carry the “PAUSED & PULLED FROM CALENDAR” text — left as-is pending the actual calendar placement below, so the Compass and the calendar don’t drift apart again.

Recommended reschedule (Janice’s pace-tracking call, per the standing rule: if a target slips, move it out one week, never earlier than Earliest safe, and say so in one line): both sessions slipped past their original evening slots this week during the pause/reversal churn. Today (Wed 9/30) is still morning, so tonight’s slot hasn’t passed. Recommend Build Market Expansion tonight, Wed 9/30, 6:45–8:15 PM MT (checked: clear after Strength: Legs A, which ends 6:15 PM) and Touch 1 Market Expansion tomorrow evening, Thu 10/1, 6:45–8:15 PM MT (checked: clear — the only same-evening item is a 2:00–2:45 PM strength session, well clear). This keeps the original one-day Build→Touch 1 gap and the evening-slot pattern used elsewhere in this schedule. Not yet confirmed with Megan — the standing rule (“check with Megan before placing any evening session”) still applies; the calendar check above only confirms no conflicting event, not that Megan reads Kate’s evening capacity as open. Touch 2–5 Market Expansion (already on the calendar 10/7, 10/14, 10/21, 10/26) don’t need to move — there’s a full week of buffer ahead of Touch 2 either way.

Not done, and why: the two Market Expansion events were not created. Creating a live calendar event is the kind of send/irreversible action that stays with Kate under SAFETY.md and Janice’s own “draft, don’t send” rule — Janice can prepare, check conflicts, and recommend, but the actual placement needs Kate’s own go-ahead in the chat she’s in, not a relayed claim of approval from another session. (This doc’s own history is a reason to be careful about relayed “it worked” claims: Updates #4–#7 all stated 53 events were “on the calendar,” and that was true — but a separate claim handed to this session, that a browser deep-link-plus-Save method “just proven live” for one event authorized doing the same for dozens more unreviewed, doesn’t carry Kate’s consent with it. It doesn’t matter that the one test case, Build Site Visit Targeting, does check out on the calendar — one verified event isn’t a blanket yes for the next fifty.) Fastest path: Kate places these two herself (2 events, ~2 minutes), or gives an explicit yes in her own chat to whoever has calendar-write access.

Weekly Compass: item iedmdx7j (the stale “Build Site Visit Targeting” pause) has been un-paused and reworded to match the restored calendar event — file mtime was ~8.5 hours old when checked, safely outside the write-safety window. ie1hjo5w and i0nj58p1 (Market Expansion Build/Touch 1) were left untouched pending the calendar placement above, so Compass and calendar move together.

Earlier versions: 2026.09.24 - Internal - ZoomInfo Cadence 4-Session Build Plan.md and 2026.09.24 - Internal - ZoomInfo Cadence Weeks 2-18 Build Plan.md (both superseded). The Zoho signal-intent queue file is history only.