# Cadence Build Order and Suppression Check

Prepared by: Jack, for Session 3B-ii (GTM: Sales)

Date: 2026.10.05

For: Kate, with Janice (calendar and tracker) and Marcus

Status: Proposal only. No calendar events were created or moved. Zoho was read only; nothing was changed.

## The short version

- Order: Revenue Intelligence and Market Expansion first, then Sales Transformation with Revenue Management, then Sales Performance Management with B2B Marketing, then Business Development with Digital Marketing. That is Scout’s order, run in pairs so each pair builds in rounds.

- This week comes first: Business Transformation and Sales Intelligence are live (324 and 48 enrolled). Their Touch 3 fires Thu 10/15. Both Touch 3 sessions land this week, ahead of the new builds.

- Market Expansion fix: the Wed 10/7 “Touch 2 Market Expansion” slot becomes Build Revenue Intelligence. Market Expansion builds Fri 10/9, Touch 1 Mon 10/12, Touch 2 Tue 10/13.

- All 54 remaining sessions finish Thu 11/19, at 1 to 2 a day, five weeks ahead of the old 12/23 finish.

- Switch-ons, one a week: Revenue Intelligence Tue 10/13, Site Visit Targeting Tue 10/20 (already set), Market Expansion Tue 10/27, Sales Transformation Tue 11/3, Revenue Management Tue 11/10, Sales Performance Management Tue 11/17, then B2B Marketing 12/1, Business Development 12/8 and Digital Marketing Tue 1/5/2027.

- Suppression check: none of the beta-partner contacts (Noble Investment Group, Raines, Crescent, PM Hotel Group, Sandpiper, Midas) is in any cadence or tagged for one. The “five Noble contacts tagged Digital Marketing” are at Noble Corporation, an offshore drilling company. ZoomInfo filed them under a Noble Investment Group account record. They are not beta contacts, but all five are sitting enrolled in the old Digital Marketing cadence, which holds a gap for later (see below).

- The suppression list is still the gate. Today’s exclusions cover two cadences only and miss four Noble Investment Group people plus Sandpiper and Midas entirely. The fix is one checkbox field, one workflow rule and one line per cadence. About 45 minutes, done by Kate in Zoho.

## What the schedule follows

- Live cadences, real fire dates. BT Auto-Enroll Live (switched on 10/1) and SI Auto-Enroll (published 9/30) both send every 7 days. Touch 3 fires Thu 10/15, Touch 4 Thu 10/22, Touch 5 Thu 10/29. Each touch is built at least 2 days before it fires. Today those touches hold the approved holding copy, so nothing stale sends if a session slips, but the real copy should win.

- Kate’s switch-on rule. A cadence switches on only when Build and Touch 1 are done and every later touch will be built at least 2 days before the first contact reaches it. New cadences are assumed to follow the BT and SI pattern: Touch 1 on switch-on, then every 7 days. So Touch 2 must be built by switch-on +5 days, Touch 3 by +12, Touch 4 by +19 and Touch 5 by +26.

- 7-day spacing between switch-ons, one new cadence a week, keyed off Site Visit Targeting on Tue 10/20.

- Rounds, not serial. Topics build in pairs, and within a pair each step goes out for both before the next step starts.

- Kate still says go. Every switch-on date below is the earliest safe date, not a trigger. Nothing publishes without the Switch-On Checklist complete and Kate’s in-the-moment yes.

## Build order: where I agree with Scout and where I adjust

I agree with Scout’s ranking. The changes are about timing and pairing, one line each.

- BT and SI Touch 3 go first this week. 372 live contacts get Touch 3 on 10/15, and next week loses time to the Wylie call (Mon) and the Hyatt McCormick Place meeting (Tue).

- Revenue Intelligence before Market Expansion. RI is a 13-contact pool with a half-reusable build, so it can be switched on first (10/13) and start producing replies while Market Expansion catches up.

- Market Expansion Touch 2 comes off Wed 10/7. Build and Touch 1 are not done. The slot becomes Build Revenue Intelligence, and Market Expansion runs Build 10/9, Touch 1 10/12, Touch 2 10/13.

- Sales Transformation pairs with Revenue Management. Both speak to the same commercial leader (PM Hotel Group’s profile, for one), and building them side by side keeps the Revenue Management copy honest about the placing line: revenue management decides tonight’s rate, the Revenue Growth System decides where next year’s growth comes from.

- B2B Marketing switches on 12/1, not Thanksgiving week. A Tue 11/24 first touch lands in the emptiest inboxes of the quarter.

- Digital Marketing switches on after New Year (Tue 1/5/2027). It is the biggest pool (711 tagged), the least specific, and its old cadence already holds dormant enrollments that must be cleared first. A 12/15 start would run its touches through Christmas.

- Sales Transformation has a history to respect. On 9/28 it sent its old Touch 1 to 100 contacts (86 delivered). Those people should start fresh at Touch 1 of the new build, or be held out, which is Kate’s call at switch-on.

## Day-by-day build schedule

Times follow the existing pattern: the evening Zoho slots this week (7:30 to 9:00 PM, after strength), then the standard morning slots, with a second session after. Janice confirms the exact times against the calendar and Megan’s read on evenings before anything is placed.

### Week of 10/5 (Colorado, flying home Thu)

| Day | Session 1 | Session 2 | Why here |
| --- | --- | --- | --- |
| Tue 10/6 | Touch 3 Sales Intelligence |  | Already on the calendar. Fires 10/15 |
| Wed 10/7 | Build Revenue Intelligence (replaces Touch 2 Market Expansion) |  | The fix. RI is the smallest build |
| Thu 10/8 | Touch 3 Business Transformation |  | Stage 3 “navigator” message locked 10/1. Fires 10/15 |
| Fri 10/9 | Build Market Expansion | Touch 1 Revenue Intelligence | Round 1 of the pair |

### Week of 10/12

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/12 | Touch 1 Market Expansion | Touch 2 Revenue Intelligence, plus the RI switch-on checklist | Wylie Center call. RI must be ready for 10/13 |
| Tue 10/13 | Touch 2 Market Expansion |  | Hyatt McCormick Place meeting. One session. RI earliest switch-on |
| Wed 10/14 | Touch 4 Business Transformation | Touch 4 Sales Intelligence | Both fire 10/22 |
| Thu 10/15 | Touch 3 Revenue Intelligence | Touch 3 Market Expansion | BT and SI Touch 3 send today |
| Fri 10/16 | Build Sales Transformation |  | Start of the next pair |

### Week of 10/19

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/19 | Build Revenue Management | Touch 1 Sales Transformation |  |
| Tue 10/20 | Touch 5 Business Transformation | Touch 1 Revenue Management | Site Visit Targeting switch-on day (Kate’s 10/20) |
| Wed 10/21 | Touch 5 Sales Intelligence | Touch 4 Revenue Intelligence | Flying Horse and O’Rourke call 11:30. Use 12:00 to 1:30 |
| Thu 10/22 | Touch 4 Market Expansion | Touch 2 Sales Transformation |  |
| Fri 10/23 | Touch 2 Revenue Management |  |  |

### Week of 10/26

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/26 | Touch 5 Revenue Intelligence (completes) | Touch 5 Market Expansion (completes) | Kate & Do runs 9:30 to 10:30. Use 10:30 on |
| Tue 10/27 | Touch 3 Sales Transformation | Touch 3 Revenue Management | Market Expansion switch-on |
| Wed 10/28 | Build Sales Performance Management | Build B2B Marketing | Start of the third pair |
| Thu 10/29 | Touch 1 Sales Performance Management | Touch 1 B2B Marketing |  |
| Fri 10/30 | Touch 4 Sales Transformation |  |  |

### Week of 11/2

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/2 | Touch 4 Revenue Management | Touch 5 Sales Transformation (completes) |  |
| Tue 11/3 | Touch 5 Revenue Management (completes) | Touch 2 Sales Performance Management | Sales Transformation switch-on |
| Wed 11/4 | Touch 2 B2B Marketing | Touch 3 Sales Performance Management |  |
| Thu 11/5 | Touch 3 B2B Marketing | Build Business Development |  |
| Fri 11/6 | Build Digital Marketing |  | Start of the last pair |

### Week of 11/9

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/9 | Touch 4 Sales Performance Management | Touch 4 B2B Marketing | Wylie Center call 10:00 to 10:30. ROI checkpoint day |
| Tue 11/10 | Touch 1 Business Development | Touch 1 Digital Marketing | Revenue Management switch-on |
| Wed 11/11 | Touch 5 Sales Performance Management (completes) | Touch 5 B2B Marketing (completes) |  |
| Thu 11/12 | Touch 2 Business Development |  | Hyatt McCormick Place meeting. One session |
| Fri 11/13 | Touch 2 Digital Marketing |  |  |

### Week of 11/16

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/16 | Touch 3 Business Development | Touch 3 Digital Marketing |  |
| Tue 11/17 | Touch 4 Business Development | Touch 4 Digital Marketing | Sales Performance Management switch-on |
| Wed 11/18 | Touch 5 Business Development (completes) |  | Flying Horse and O’Rourke call. Use 12:00 to 1:30 |
| Thu 11/19 | Touch 5 Digital Marketing (completes) |  | All topics built |

Count: 54 sessions (BT 3, SI 3, eight new topics at 6 each). Fridays carry one session so a slipped day has somewhere to land. If two sessions slip in the same week, the pair after it moves out one week, and the switch-on dates behind it move with it.

## Earliest safe switch-on by topic

“Math earliest” is the first day every touch would be built at least 2 days ahead. “Recommended” adds the one-a-week spacing and the holiday calls above.

| Topic | Build and Touch 1 done | Touch 5 done | Math earliest | Recommended switch-on |
| --- | --- | --- | --- | --- |
| Business Transformation | Live 10/1 | Tue 10/20 | Live | Live. Keep touches ahead of 10/15, 10/22, 10/29 |
| Sales Intelligence | Live 9/30 | Wed 10/21 | Live | Live. Same fire dates |
| ABM | Built through | Built through | Live | Live |
| Site Visit Targeting (router) | Built 9/30 | n/a | Tue 10/20 | Tue 10/20 (Kate’s date, unchanged) |
| Revenue Intelligence | Fri 10/9 | Mon 10/26 | Mon 10/12 | Tue 10/13 |
| Market Expansion | Mon 10/12 | Mon 10/26 | Tue 10/13 | Tue 10/27 |
| Sales Transformation | Mon 10/19 | Mon 11/2 | Tue 10/20 | Tue 11/3 |
| Revenue Management | Tue 10/20 | Tue 11/3 | Wed 10/21 | Tue 11/10 |
| Sales Performance Management | Thu 10/29 | Wed 11/11 | Fri 10/30 | Tue 11/17 |
| B2B Marketing | Thu 10/29 | Wed 11/11 | Mon 11/2 | Tue 12/1 |
| Business Development | Tue 11/10 | Wed 11/18 | Wed 11/11 | Tue 12/8 |
| Digital Marketing | Tue 11/10 | Thu 11/19 | Wed 11/11 | Tue 1/5/2027 |

Before every new switch-on (the same checklist BT and SI went through):

- The beta suppression field on the cadence’s view and in its un-enroll criteria (next section)

- Un-enroll on reply and on Meeting Booked, both OR’d (Kate’s 10/1 rule for every new cadence)

- A fresh Auto-Enroll cadence, published with existing records included and everyone starting at Touch 1. Never reactivate an old cadence; the old Phase 1 cadences hold stale enrollments

- No [PLACEHOLDER] anywhere, and all five templates test-sent to Mr. Testy

- Check the real step delays in Zoho match Touch 1 then every 7 days

- Kate’s yes on the day

## Suppression check: what is in Zoho today

How it was checked (read only, 2026.10.05): Contacts searched by account name and by email domain for all six accounts, the named buyers searched by last name, and the Leads module searched by company and domain (no Leads found). For every record found, the Cadences related list was read, which shows every cadence the person has ever been enrolled in, live or not. ZI Intent Topic, ZI Workflow Source, Tag and SVT Choice were read on each.

### Beta-account contacts in Zoho: none are in a cadence

| Account | Contact | Email | Account link | Intent tag | Cadences |
| --- | --- | --- | --- | --- | --- |
| Noble Investment Group | Mit Shah, CEO | mitesh.shah@nobleinvestment.com | Noble Investment Group | None (tags: Engaged, Ignite, Industry; Investor) | None |
| Noble Investment Group | Ben Brunt | ben.brunt@nobleinvestment.com | None | None | None |
| Noble Investment Group | Dustin Fisher, SVP Investments | dustin.fisher@nobleinvestment.com | Noble Investment Group | None | None |
| Noble Investment Group | Emily Feeney | emily.feeney@nobleinvestment.com | Noble Investment Group | None | None |
| Noble Investment Group | Dan Konzelmann | daniel.konzelmann@nobleinvestment.com | None | None | None |
| Noble Investment Group | George Dabney | george.dabney@nobleinvestment.com | None | None | None |
| Noble Investment Group | “Katie Minnock” | mariah.howard@nobleinvestment.com | None | None | None |
| PM Hotel Group | Joseph Bojanowski, President | jbojanowski@pmhotelgroup.com | PM Hotel Group | None (tag: In Active) | None |
| Raines | Kerry Ranson | kranson@hp-hotels.com | None | None | None |
| Crescent Hotels & Resorts | Treana Armstrong, VP Technology | treana.armstrong@crescenthotels.com | Crescent Hotels & Resorts | None | None |
| Sandpiper Hospitality | Carter Rise | crise@sandpiper.us.com | None | None | None |
| Midas Hospitality | No record |  |  |  |  |

Not in Zoho at all: Stephen Nicholas, Erica Lipscomb, Kirk Pederson, Dawn Gallagher, Lilian Hu, John Barrar. Linda Eigelberger exists only as an old IHG record (linda.eigelberger@ihg.com, tag In Active, no cadence).

Nobody on the list carries the SVT Approved tag, a Site Visit Targeting source or an SVT Choice, so none is in the 10/20 router send or the three “From Site Visit” cadences. None is in ABM, ABM Auto-Enroll, BT Auto-Enroll Live or SI Auto-Enroll.

### What Scout’s two flags turned out to be

“Five Noble contacts tagged Digital Marketing.” They are real, tagged and enrolled, but they are not Noble Investment Group. All five have noblecorp.com emails: Noble Corporation, the offshore drilling company. ZoomInfo attached them to one of the three “Noble Investment Group” account records, the one whose website field reads www.noblecorp.com.

| Contact | Email | Intent tag | Cadence | Status |
| --- | --- | --- | --- | --- |
| Robert Eifler, President and CEO | reifler@noblecorp.com | Digital Marketing | Digital Marketing | Enrolled, Ongoing since 9/24, next step Scheduled |
| Jason McMullen, VP and CIO | jmcmullen@noblecorp.com | Digital Marketing | Digital Marketing | Enrolled, Ongoing since 9/24, next step Scheduled |
| Claus Bachmann, VP | cbachmann@noblecorp.com | Digital Marketing | Digital Marketing | Enrolled, Ongoing since 9/24, next step Scheduled |
| Joanna Jakielska, Reporting Services Head | jjakielska@noblecorp.com | Digital Marketing | Digital Marketing | Enrolled, Ongoing since 9/24, next step Scheduled |
| Sonia Gilham, Direct Category Management Head | sgilham@noblecorp.com | Digital Marketing | Digital Marketing | Enrolled, Ongoing since 9/24, next step Scheduled |

The Digital Marketing cadence has been off since the 9/28 shutdown, so nothing is sending. Two consequences:

- No beta risk from these five. But the account-name exclusion on BT and SI treats them as Noble Investment Group, and anyone at Noble Corp would be suppressed by mistake.

- A restart risk for all of Digital Marketing. The old cadence still holds enrollments marked Ongoing with a scheduled next step. If it is ever switched back on, those people fire from where they sit, on old Phase 1 copy. Build Digital Marketing as a fresh cadence and leave the old one off. The same check belongs on every old Phase 1 cadence before its replacement goes live.

“PM Hotel Group shows on four KB&Co cadence topics.” That is ZoomInfo intent at the company level. Inside Zoho, PM Hotel Group has no intent-tagged contact. The risk is the next sync: PM is surging on Revenue Intelligence, Sales Transformation, Revenue Management, Sales Intelligence and B2B Marketing, so ZoomInfo is likely to push Erica Lipscomb or a peer into Zoho with one of those tags. Revenue Intelligence switches on first (10/13), so it needs the suppression before then.

### Record problems found along the way (no changes made)

- Ethan Kramer (ekramer@paramounthotelgroup.com) is linked to PM Hotel Group but works at Paramount Hotel Group. The account-name exclusion would suppress him by mistake.

- John Smith (john.smith@crescentcourt.com) sits under “Hotel Crescent Court,” a different company. Any “contains Crescent” rule would catch him.

- “Katie Minnock” has the email mariah.howard@nobleinvestment.com. The name and email do not match; verify before Jack uses it.

- Four Noble Investment Group people, Kerry Ranson and Carter Rise have no account link, so account-name exclusions cannot see them.

## The suppression list: what it needs and the fastest way to build it

### What it must contain

Key it on email domain, not account name. Domains are what ZoomInfo cannot misfile, and they catch new people (Erica Lipscomb, Stephen Paul, John Barrar) the day they arrive.

| Account | Domain(s) | Source |
| --- | --- | --- |
| Noble Investment Group | nobleinvestment.com | Seen in Zoho |
| PM Hotel Group | pmhotelgroup.com | Seen in Zoho |
| Raines | hp-hotels.com, plus Raines’ current domain | hp-hotels.com seen in Zoho; confirm the Raines domain in ZoomInfo |
| Crescent Hotels & Resorts | crescenthotels.com | Seen in Zoho |
| Sandpiper Hospitality | sandpiper.us.com | Seen in Zoho |
| Midas Hospitality | midashospitality.com | Midas website; confirm the email domain in ZoomInfo |

Do not add noblecorp.com, paramounthotelgroup.com or crescentcourt.com. Add a backup’s domain (Hawkeye, for one) only on the day it becomes a beta target.

### Fastest way to build it (Kate in Zoho, about 45 minutes)

This mirrors the Meeting Booked stop built on 10/1, so the pattern is already proven in this org.

- Make one checkbox on Contacts (and Leads): “Ignite Beta Hold.”

- One workflow rule on Contacts, on Create or Edit: if Email contains any of the domains above, tick Ignite Beta Hold. This catches every future ZoomInfo arrival automatically.

- Tick the 11 existing records by mass update (search each domain in Contacts, select all, Mass Update). The rule only fires on new edits, so the existing records need this once.

- One criterion on every auto-enroll view: “Ignite Beta Hold is not selected.” Views today: BT Auto-Enroll ZI Intent Topic, Sales Intelligence Contacts, ABM Auto-Enroll (ZI Workflow Source), the ABM - ZI filter, the three SVT Chose views, and Market Expansion’s. Every new topic view gets it at Build.

- One un-enroll criterion on every live cadence: “Ignite Beta Hold is selected,” OR’d with reply and Meeting Booked, on ABM, ABM Auto-Enroll, BT Auto-Enroll Live, SI Auto-Enroll and the three From Site Visit cadences. That removes anyone who slips in before the view catches them.

- Upstream, in ZoomInfo: add the six companies to the exclusion list on the intent and Site Visit Targeting workflows, so they stop syncing with topic tags at the source.

- Then retire the account-name and hp-hotels.com exclusions on the BT and SI views, once the field is in place, so Noble Corp and Paramount contacts are not suppressed by mistake.

Deadline: before Revenue Intelligence switches on (Tue 10/13). If it is not done by Mon 10/12, Revenue Intelligence waits a week.

Agents have been blocked from CRM configuration changes in this org, so steps 1 to 5 are Kate’s, or a session she gives an in-the-moment yes. Step 3 and step 6 are the only ones that take any real clicking.

## For Janice

- The calendar still shows “Zoho: Touch 2 Market Expansion” on Wed 10/7 and the old 13-week labels from 10/12 on. Relabel to this schedule once Kate approves it. Nothing was moved here.

- The Cadence Turn-On Tracker’s dates for every topic after Site Visit Targeting are superseded by the table above once Kate approves.

- Market Expansion’s old earliest-safe date (Tue 10/13) no longer holds; it is Tue 10/27 under this plan.