# Compass Reconciliation, weeks of 9/28 and 10/5

Janice, Monday 2026.09.28, 10:33 PM MT. This is last night’s 8:15 PM run. It stalled and only ran now, so Monday is already behind us.

Times are Mountain unless marked. You’re in Colorado and the machine clock is on MT. The calendar connector returns MT as well.

The Compass file: last saved at 6:34 AM, 16 hours before this run, so I wrote to it. I backed it up first. The save time was 6:34 AM right before my write and 10:40 PM right after, which is my own write. Nothing else changed the file in between. If you have the Compass page open from this morning, reload it before you edit, or the page will save over my two lines.

Heads up: two sessions are live right now (“Touchpoint 2 business transformation” and “Business transformation Zoho workflow”). The Master Schedule changed at 10:33 PM. Anything decided in those sessions after that time is not in this report.

Second pass, 11:20 PM MT. The task fired again after this report was written. Nothing in OneDrive changed after 10:41 PM, and both live sessions went quiet at 10:43 PM. I made no second write to the Compass, because the only recent change to the file was my own and there was nothing new to add. One thing from the transcripts bears on decision 2 below: - Market Expansion may have been built after all. A 9/23 to 9/24 Zoho session (“Sales automations intent signals”) typed a cadence named “Market Expansion Cadence - Intro” in Zoho. A 9/27 session logged “Market Expansion cadence paused.” Tonight’s Business Transformation session refers to “the laptop session that originally built the Market Expansion cadence.” - Jack checked files only, and Zoho’s connector can’t read cadences. So his “no rebuild” finding and the Master Schedule’s “done 9/24” can both be partly right: the cadence exists in Zoho, but nobody wrote it to a file. - Please look in Zoho before Wed 9/30. If it’s there with Touch 1, Wednesday is Touch 2 and Thursday frees up for Site Visit Targeting.

## What does not foot

Hours foot now. businessDevelopment for 9/28 is 9 hrs against 9 hrs of tasks. For 10/5 it is 6.75 hrs against 6.75 hrs, after I added the LinkedIn post. No other category has a target.

The Master Schedule and the Compass disagree about this week and next. - Thu 10/1: - Master Schedule (update #3, tonight): Site Visit Targeting grid + revamped Touch 1. - Compass and calendar: Touch 1 Market Expansion. - Thursday has no open time for both. - Market Expansion: - Master Schedule: Build + Touch 1 done 9/24. Wed 9/30 is Touch 2 and Wed 10/7 is Touch 3. - Compass and calendar, per Jack’s check: Build Wed 9/30 and Touch 1 Thu 10/1, then Touch 2 on 10/7. - Jack found no file showing Market Expansion was ever rebuilt. - Session count: the Master Schedule still says 59. If Jack is right about Market Expansion, it’s 61 before Site Visit Targeting is added. - The Master Schedule also contradicts itself on the finish date: - Tue 12/22, in the “net effect” and “status” lines. - Wed 12/23, in update #3 and the week 13 table. - The .md (10:33:21 PM) and the .docx (10:33:31 PM) carry the same split, so the two copies agree with each other.

Stale lines in the Compass. I left them for you to confirm: - 9/28 and 10/5 businessStrategy still say “OPEN, Tue/Thu evenings.” You settled that on 9/28: Megan’s strength first, then the build at 7:30. - 10/5 says “Confirm the Week 1 suppression-list build shipped.” You parked the suppression list until Ignite outreach starts. - 9/28 delivery shows “Wylie: Monthly Call, Fri, 60 min.” The Wylie Performance Review is no longer on Friday. It’s now Wed 10/7, 10:30 to 12:00, tentative. It isn’t in the 10/5 Compass. - Wylie Plan: 60 min on the calendar, 30 min in the Week of 9/28 schedule doc, and no duration in the Compass.

## Day by day against the calendar

Rest of the week of 9/28 - Tue 9/29: fits. SearchAtlas 10:15, Wylie Plan 11:30, Flying Horse sync 3:00, strength 6:30, Zoho 7:30. - Wed 9/30: fits, with no slack from 9:00 to 1:30. The Exec Meeting, Lodge, Wylie Report and SearchAtlas Day Two run back to back. - Thu 10/1: full, and there’s no flight home on the calendar. - Wed night you’re building in Colorado. Thursday starts in Dallas at 10:00 CT. - The day holds Dallas, nails, Ignite with Tristan, Touch 1 Market Expansion, the AIR happy hour, strength and packing. - Adding the Site Visit Targeting build means something comes off. - Fri 10/2 to Sun 10/4: drive days and the Michigan weekend. They match the plan. The Friday calls (Ignite 10:30 CT, Hotel Evolution 1:30 CT) are taken from the car, as you decided.

Week of 10/5 - Mon 10/5: Michigan in the morning. Touch 3 Business Transformation 10:00 to 11:30, Sales and Marketing 2:00 to 3:00, airport 3:00, flight 4:00. - The LinkedIn post placeholder (2:00 to 2:45) collides with Sales and Marketing. - 11:30 to 2:00 is open. Post there, and only if the landing page is live. - Tue 10/6: light in the day, Zoho at 7:30. - The Site Visit Targeting one-time send is targeted for 9 AM ET (7 AM MT). It depends on Thursday’s build and on your reply to the one person who answered. - Wed 10/7: the Wylie Performance Review (10:30 to 12:00, tentative) overlaps the Lodge Weekly Revenue meeting (10:30 to 11:00). - Thu 10/8: Ignite with Tristan (1:00 to 2:00) sits on top of airport check-in (1:00 to 2:00). The flight is at 2:00. The Revenue Intelligence build at 10:00 is fine. - Fri 10/9: the Thursday flight home answers last week’s question about getting to Frisco. The Ignite call (10:30 to 11:00 CT) still sits inside the Advancement Board (9:00 to 11:30 CT, in person).

## Carried untimed two weeks or more

- Advisory Strategy execution: 9/21, 9/28, 10/5. That makes three weeks.

- Flying Horse Automation 3 (HubSpot): 9/21, 9/28, 10/5

- Cash-need pass (S5): 9/28, 10/5

- Debt (personal): 9/21, 9/28, 10/5

- Ignite Sales and Marketing: timed on 9/28, untimed again on 10/5

Real movement on Wendy’s flag. Founding-partner pricing, the lawyer, Kisaco, the SI Stage 5 client, the Eddie call, onboarding waves and NYU / AHLA / Hunter all have drive-day slots on Fri 10/2 and Sat 10/3. They’re still listed again, untimed, in 10/5. Once you decide on the drive, they come off Monday’s list.

## What I captured into the Compass

- 10/5, businessDevelopment: Mon, 45 min. Post the Sales Intelligence “Right, or lucky?” piece to LinkedIn, and confirm the landing page and Zoho Form are live first. hoursTarget went from 6 to 6.75.

- 9/28, businessDevelopment > Zoho: Site Visit Targeting grid + revamped Touch 1. I left it untimed and didn’t pick a day. Hours are unchanged.

Nothing else was written. I left the stale lines above alone.

## Needs a revisit date from you

Parked in the Session Handoff log, new entry dated 2026.09.28 (late).

- Site Visit Targeting one-time send, target Tue 10/6. It’s not in the Compass.

- Finishing and publishing the right-or-just-lucky landing page and form before 10/5. There’s no owner and no slot.

- Wylie Performance Review, now 10/7. It’s not in the 10/5 Compass.

- The 17 items from the 9/27 parking lot. None has a date yet.

## Needs your decision

- Thu 10/1: Site Visit Targeting or Touch 1 Market Expansion? Or does one of them move to the weekend or the drive?

- Market Expansion: done or not? Your answer decides whether the Master Schedule gets rebuilt at 61 sessions. It also decides the finish date, 12/22 or 12/23 or later.

- How do you get from Colorado to Dallas before Thursday 10:00 CT? There’s no flight on the calendar.

- Mon 10/5: when does the LinkedIn post go out? 11:30 to 2:00 is open. Who finishes the landing page before then?

- Wed 10/7: the Wylie review or the Lodge meeting for 10:30 to 11:00.

- Thu 10/8: move the Tristan call, or leave for the airport later.

- Fri 10/9: skip Ignite or step out of the Board.

- Stale lines: OK to clear the Tue/Thu “OPEN” line and the suppression-list confirm line from 10/5?

## Lane notes

- Megan (workouts): 9/28 still has both sets of blocks. The strength subtasks still say “CONFLICT: ZoomInfo build holds this slot,” which your 9/28 call resolved. That cleanup is hers. I didn’t touch it.

- Marcus (does it belong):

  - Site Visit Targeting’s move up traces to Session 6 (the intent cadence build).

  - The landing page traces to the Sales Intelligence motion series.

  - SearchAtlas Day One and Day Two still have no named Master Plan session.

- Wendy (categories): admin is empty in both weeks. Accounting has been missing since 9/21.

## Housekeeping

- Nothing from this run was written to the calendar. The calendar write is still broken, so the items above are listed for you to add.

- The Zoho queue file is now marked superseded for build order. It no longer disagrees with the Master Schedule.