# Compass Reconciliation, week of 10/5

Janice, Monday 2026.10.05, 9:00 AM Eastern. Last night’s 8:15 PM run didn’t fire, so this is the catch-up. Monday morning is already underway.

Times are Mountain unless marked. The calendar connector returns Mountain. You’re in Michigan today (machine clock is Eastern), so add 2 hours for your local time today.

The Compass file: last saved Wed 9/30 at 9:34 AM, nothing since. I wrote three lines to the week of 10/5 at 9:00 AM Eastern and checked the save time before and after. Only my write changed it. If you have the Compass page open from earlier, reload it before you edit, or the page will save over my lines.

## What does not foot

Business Transformation and Sales Intelligence are already sending, but the Compass says they switch on 10/6 and 10/8. - The 10/2 brief, reading the Turn-On Tracker (updated 10/1), says Sales Intelligence switched on Wed 9/30 (48 enrolled) and Business Transformation on Thu 10/1 (324 enrolled). - The Master Schedule (9/30) and the 10/5 Compass “LOCKED NUMBERS” line still say 10/6 and 10/8. The Tracker is the newer file. - That line also says Jack’s Deal-logging has to be running by 10/6 “when real sends begin.” Sends began 10/1. - Your build-pace rule: the brief puts Touch 3 at about 10/15 and 10/16, so Touch 3 on 10/5 and 10/6 is in time. Touches 4 and 5 depend on the real step delays in Zoho. If the cadences use the tight Path A spacing (Days 1, 4, 8, 11, 16), Sales Intelligence Touch 4 sends 10/10 and Touch 5 sends 10/15, before their 10/13 and 10/20 builds. Please confirm the delays.

The suppression list fell out of the plan. It was a 20-minute Zoho line in 9/28. You said build it now (9/29). It isn’t in 10/5, and two cadences are live without it.

Market Expansion has no Build or Touch 1, but Touch 2 is on the calendar Wed 10/7. Both were deleted during the 9/29 pause and never put back. I found no file or session showing they happened. The 9/28 Compass still shows them as “pulled.”

Site Visit Targeting Build (Thu 10/1): a session ran that day, but no output file shows it finished. Touch 1 is Thu 10/8 and depends on it.

Hours: - businessDevelopment, 10/5: 9.75 hrs target against 9.75 hrs of tasks, after the two case-study sessions I added. It was 6.75. - businessDevelopment, 9/28 (closed week): target 10.5, tasks 10.8 hrs. That includes 3 hrs of “do NOT run” paused lines. Without them it’s 7.8 hrs. - No other category has a target.

Source docs: the Master Schedule .md and .docx match this week (both 9/30, both 60 sessions left, finish 12/23).

Stale lines in 10/5, left for you to confirm: - “LOCKED NUMBERS” (switch-on dates, ABM-only, Deal-logging deadline). See above. - The LinkedIn post says “11:30 to 2:00, after Touch 3 BT.” Touch 3 BT moved to 11:30 to 1:00. The post’s flag in flagged-priorities was also re-keyed to Sales Intelligence switch-on day, which per the Tracker was 9/30. Has it posted? Is right-or-just-lucky live?

## Day by day against the calendar

- Mon 10/5 (Michigan): over by about an hour.

  - AC refresher 7:00 to 8:30, FEI ActiveCampaign training 9:30 to 10:30, Hotel Evolution 10:30 to 11:30, Touch 3 BT 11:30 to 1:00.

  - Sales and Marketing (2:00 to 3:00) sits on top of airport check-in (2:00 to 3:00). Flight at 3:00.

  - The LinkedIn post (45 min) has only 1:00 to 2:00, which is also the drive to the airport.

- Tue 10/6: fits. Expedia 8:00, SearchAtlas town hall 9:00, Flying Horse forecast 11:00 (tentative), Case Studies ABM 1:00 to 2:30, strength 6:30, Touch 3 SI 7:30 to 9:00.

- Wed 10/7: fits, no buffer in the evening. Exec Meeting 9:00, Wylie review 10:30 to 12:00 (you’re skipping the Lodge meeting, which is still on the calendar), Case Studies Revenue 1:00 to 2:30, strength 6:30 to 7:15, Touch 2 Market Expansion 7:30.

- Thu 10/8: Ignite with Tristan (1:00 to 2:00) still sits on airport check-in (1:00 to 2:00). Flight 2:00. Flagged last week, not moved.

- Fri 10/9 (Dallas): the Ignite call (10:30 to 11:00 CT) still sits inside the Advancement Board in Frisco (9:00 to 11:30 CT). Flagged last week, not moved. The “20 minutes with Kate & Co.” at 11:45 CT is your own test booking.

- Sat 10/10 and Sun 10/11: fit. Training per Megan. Weekly Planning 6:00 PM CT, Strategy Session 7:00 PM CT.

## Carried untimed two weeks or more

- Advisory Strategy execution: 9/21, 9/28, 10/5

- Flying Horse Automation 3 (HubSpot): 9/21, 9/28, 10/5

- Debt (personal): 9/21, 9/28, 10/5

- Cash-need pass (S5): 9/28, 10/5

- Founding-partner pricing and Kisaco leads: 9/28, 10/5. Both had drive slots Fri 10/2 and Sat 10/3. I found no dictation file from Saturday, so I can’t tell what you decided.

- Wylie Plan: 9/28, 10/5

## What I captured into the Compass (week of 10/5)

- businessDevelopment: Case Studies ABM session with Maxell, Tue, 90 min.

- businessDevelopment: Case Studies Revenue session with Maxell, Wed, 90 min. hoursTarget 6.75 to 9.75.

- delivery, FEI: ActiveCampaign training, Mon, 60 min.

All three were on your calendar and missing from the Compass. Nothing else was changed. The stale lines above are untouched.

Not built yet: week of 10/12. For Sunday, from the Master Schedule: - Mon 10/12: Touch 4 Business Transformation, 9:30 to 11:00 (Wylie Center call at 11:00) - Tue 10/13: Touch 4 Sales Intelligence (Hyatt McCormick meeting 10:00 to 12:00, you work through it) - Wed 10/14: Touch 3 Market Expansion (only if Build, Touch 1 and Touch 2 have happened) - Thu 10/15: Touch 2 Site Visit Targeting - Admin, Tue 10/13: upgrade Zoho Bookings to Basic before the trial ends (flagged priority)

## Needs a revisit date from you

Parked in the Session Handoff log, new entry dated 2026.10.05.

- Suppression list build (overdue, see above)

- Build Market Expansion and Touch 1 Market Expansion

- Weekly LinkedIn post (Business Transformation), in 9/28 and gone from 10/5

- Wylie Monthly Report: done?

- The drive-day decisions, if they weren’t settled on the drive

- right-or-just-lucky page: owner and date

- The 17 items from the 9/27 parking lot

One problem with the log itself: the 9/27 and 9/28 reports both say they added parking-lot entries, and neither is in the file. Something rewrote it after those runs. I wrote all 17 items out in full this time instead of pointing back to the old reports.

## Needs your decision

- Suppression list: when, and who? It needs Zoho permissions, so likely you.

- Market Expansion: build it before Wed 10/7, or make Wednesday the Build and move Touches 1 to 5 out a week?

- Switch-on dates: OK to update the “LOCKED NUMBERS” line to 9/30 and 10/1? And can you confirm the real step delays so I can check Touches 4 and 5 against the build dates?

- Mon 10/5: Sales and Marketing or an on-time airport arrival. And does the LinkedIn post move?

- Thu 10/8: move the Tristan call, or leave for the airport later.

- Fri 10/9: skip Ignite or step out of the Board.

- Hotel Evolution: two calls this week (Mon and Fri) and no delivery line. Add it as a client?

## Lane notes

- Megan (workouts): the 10/5 workouts category is a stub (cardio Tue, Wed, Thu, Sat, Sun; strength Sun). Her 10/4 plan is 4 strength and 4 cardio at set times. 9/28 still has both sets of blocks. That cleanup is hers, and I didn’t touch it.

- Marcus (does it belong): the case-study sessions trace to the 3B-i website audit and the 9/29 site restructure plan. Hotel Evolution and the SearchAtlas town hall have no Master Plan anchor on file.

- Wendy (categories): admin is empty for the third week running. Accounting has been missing since 9/21.

## Housekeeping

- Nothing was written to the calendar. Megan’s 7 sessions for the week are in her 10/4 file for you to add.

- This run fired Monday at 8:56 AM Eastern instead of Sunday at 8:15 PM Central.