# Cadence Build Timeline Reset

Prepared by: Jack, for Kate (Janice places it on the calendar once you say yes)

Date: Sunday 2026.10.11

Status: Proposal. Nothing on the calendar or in Zoho has been changed by this doc. Times are Mountain unless marked.

## The short version

- Losing Thursday and Friday costs about three working days, not a month. The finish moves from Thu 11/19 to Tue 11/24, and Thanksgiving week stays clear after that.

- Every switch-on date holds except Revenue Intelligence, which Janice already moved from 10/13 to Tue 10/20.

- The live cadences come first. Business Transformation and Sales Intelligence Touch 4 fire Thu 10/22 to 372 people, and neither one is on your calendar yet. I put them on Mon 10/12 and Fri 10/16, well ahead of the Tue 10/20 deadline.

- This week stays light on purpose. Five cadence sessions around Colorado, the owner meetings, Flying Horse and FEI. No weekend sessions.

## What slipped

These were planned for the week of 10/5 and 10/12 and are not done or not placed:

- Build Revenue Intelligence and Build Market Expansion (Janice moved both to Tue 10/13)

- Touch 1 Revenue Intelligence (moved to Thu 10/15)

- Touch 1, 2 and 3 Market Expansion, Touch 2 and 3 Revenue Intelligence (dropped off the calendar)

- Touch 4 Business Transformation and Touch 4 Sales Intelligence (dropped off the calendar, and these are the ones that matter most)

- Build Sales Transformation (Fri 10/16)

Still due today, already on your calendar: the BT Touch 3 readback (3:00) and publishing the signal-to-result page for SI Touch 3 (3:30). That page was still a 404 this morning, and Touch 3 sends this week.

## The new order

Same pairs, same rounds. Revenue Intelligence and Market Expansion finish their rounds next week, and every pair behind them starts about one week later than planned. Fridays still carry one session so a slipped day has somewhere to land.

### Week of 10/12 (Colorado Mon to Thu, Dallas Fri)

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/12 | Touch 4 Business Transformation, 11:45 to 1:15 |  | New. After the Wylie call, before the Wylie report |
| Tue 10/13 | Build Revenue Intelligence (already placed) | Build Market Expansion (already placed) | Owner pre-meetings all day |
| Wed 10/14 |  |  | No cadence session. Owner meetings, FEI Session 2, Flying Horse Session 2 |
| Thu 10/15 | Touch 1 Revenue Intelligence (already placed) |  | Fly home at 3:00. BT and SI Touch 3 send today |
| Fri 10/16 | Touch 4 Sales Intelligence, 1:30 to 3:00 MT (2:30 to 4:00 CT) |  | New. After Hotel Evolution |

### Week of 10/19

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/19 | Touch 1 Market Expansion | Touch 2 Revenue Intelligence |  |
| Tue 10/20 | Touch 5 Business Transformation (completes) | Touch 2 Market Expansion | Site Visit Targeting and Revenue Intelligence switch-on |
| Wed 10/21 | Touch 5 Sales Intelligence (completes) | Touch 3 Revenue Intelligence | Flying Horse and O’Rourke call 11:30 |
| Thu 10/22 | Touch 3 Market Expansion | Build Sales Transformation | BT and SI Touch 4 send today |
| Fri 10/23 | Build Revenue Management |  |  |

### Week of 10/26

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 10/26 | Touch 4 Revenue Intelligence | Touch 4 Market Expansion | Kate & Do 9:30 to 10:30 |
| Tue 10/27 | Touch 5 Revenue Intelligence (completes) | Touch 5 Market Expansion (completes) | Market Expansion switch-on |
| Wed 10/28 | Touch 1 Sales Transformation | Touch 1 Revenue Management |  |
| Thu 10/29 | Touch 2 Sales Transformation | Touch 2 Revenue Management |  |
| Fri 10/30 | Touch 3 Sales Transformation |  |  |

### Week of 11/2

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/2 | Touch 3 Revenue Management | Touch 4 Sales Transformation |  |
| Tue 11/3 | Touch 4 Revenue Management | Touch 5 Sales Transformation (completes) | Sales Transformation switch-on |
| Wed 11/4 | Touch 5 Revenue Management (completes) | Build Sales Performance Management |  |
| Thu 11/5 | Build B2B Marketing | Touch 1 Sales Performance Management |  |
| Fri 11/6 | Touch 1 B2B Marketing |  |  |

### Week of 11/9

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/9 | Touch 2 Sales Performance Management | Touch 2 B2B Marketing | Wylie call 10:00. ROI checkpoint day |
| Tue 11/10 | Touch 3 Sales Performance Management | Touch 3 B2B Marketing | Revenue Management switch-on |
| Wed 11/11 | Touch 4 Sales Performance Management | Touch 4 B2B Marketing |  |
| Thu 11/12 | Touch 5 Sales Performance Management (completes) |  | Hyatt McCormick Place meeting. One session |
| Fri 11/13 | Touch 5 B2B Marketing (completes) |  |  |

### Week of 11/16

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/16 | Build Business Development | Build Digital Marketing |  |
| Tue 11/17 | Touch 1 Business Development | Touch 1 Digital Marketing | Sales Performance Management switch-on |
| Wed 11/18 | Touch 2 Business Development |  | Flying Horse and O’Rourke call. One session |
| Thu 11/19 | Touch 2 Digital Marketing | Touch 3 Business Development |  |
| Fri 11/20 | Touch 3 Digital Marketing |  |  |

### Week of 11/23 (Thanksgiving)

| Day | Session 1 | Session 2 | Note |
| --- | --- | --- | --- |
| Mon 11/23 | Touch 4 Business Development | Touch 4 Digital Marketing |  |
| Tue 11/24 | Touch 5 Business Development (completes) | Touch 5 Digital Marketing (completes) | All topics built. Wed to Fri stay clear |

Count: 52 sessions left (47 after this week). Five this week, then 8 to 9 a week.

## Switch-on dates

The math still works for every topic: Build and Touch 1 are done before switch-on, and each later touch is built at least 2 days before the first contact reaches it.

| Topic | Build and Touch 1 done | Last touch built | Switch-on | Change |
| --- | --- | --- | --- | --- |
| Business Transformation | Live | Tue 10/20 | Live | Touch 4 and 5 now Mon 10/12 and Tue 10/20 |
| Sales Intelligence | Live | Wed 10/21 | Live | Touch 4 and 5 now Fri 10/16 and Wed 10/21 |
| Site Visit Targeting (router) | Built 9/30 | n/a | Tue 10/20 | None |
| Revenue Intelligence | Thu 10/15 | Tue 10/27 | Tue 10/20 | Was 10/13 (Janice moved it 10/11) |
| Market Expansion | Mon 10/19 | Tue 10/27 | Tue 10/27 | None |
| Sales Transformation | Wed 10/28 | Tue 11/3 | Tue 11/3 | None |
| Revenue Management | Wed 10/28 | Wed 11/4 | Tue 11/10 | None |
| Sales Performance Management | Thu 11/5 | Thu 11/12 | Tue 11/17 | None |
| B2B Marketing | Fri 11/6 | Fri 11/13 | Tue 12/1 | None |
| Business Development | Tue 11/17 | Tue 11/24 | Tue 12/8 | None |
| Digital Marketing | Tue 11/17 | Tue 11/24 | Tue 1/5/2027 | None |

One overlap to know about: Site Visit Targeting and Revenue Intelligence now both switch on Tue 10/20, which breaks the one-new-cadence-a-week spacing. I’m comfortable with it. Revenue Intelligence is 13 contacts and Site Visit Targeting is a one-touch router, so the reply load stays small. If you’d rather keep them apart, Revenue Intelligence moves to Tue 10/27 alongside Market Expansion, and nothing else changes.

These are still the earliest safe dates, not triggers. Nothing switches on without the Switch-On Checklist done and your yes in the moment.

## If another day slips

Same rule as before: if two sessions slip in one week, the pair after it moves out one week and its switch-on moves with it. The one thing that never slips is a touch for a live cadence. Those get the next open slot before anything new.

## What Janice does once you approve

- Place Touch 4 BT (Mon 10/12) and Touch 4 SI (Fri 10/16)

- Move the existing 10/19 to 11/19 Zoho sessions to the dates above, and add Tue 11/24

- Update the Cadence Turn-On Tracker and add Update #12 to the Master Schedule