## Slide 1
Advisory & Ignite — Session Status One page, printable. Full detail lives in the dependency-graph artifact and the master plan doc.
Done
In progress
Not started
S1
→
S2
→
S3A
→
S3B-i
→
S3B-ii
→
S4
→
S5
→
S6
→
S7
S1 Advisory Strategy
● DONE
Kate · Jack · Scout · Finn
3 clients × $25K = $75K new. $460.8K total Advisory revenue, EOY 2027.
NEXT: Hand to Janice for the Weekly Compass
S2 Advisory Pro Forma
● READY TO SCHEDULE
Kate · Finn · Shelby
Working pro forma that models real growth, not flat expenses.
NEXT: Convert S1's thesis into monthly revenue assumptions
S3A Ignite Strategy
● NOT STARTED
Kate + Eddie, Tristan · Scout · Finn
Confirmed partner count, near-term revenue target, capacity plan.
NEXT: ⚠ Confirm 3–5 partners — 3B already assumes this
S3B-i GTM: Marketing
● IN PROGRESS
Marcus · Kate · Scout · Maxell
Positioning locked (“Revenue Growth System”). Pitch drafted & split.
NEXT: Decide the founding-partner post-beta pricing advantage
S3B-ii GTM: Sales
● NOT STARTED
Jack · Kate · Marcus · Finn
Target list built: Noble, Raines, Crescent, PM Hotel Group.
NEXT: Draft the pilot agreement — lawyer not yet named
S4 Ignite Financial Model
● BLOCKED ON 3A
Kate + Eddie, Tristan · Finn · Shelby
Funded model, replacing 2024 assumptions. Cap table fixed.
NEXT: Remove Garrard & Tavares from the cap table
S5 Kate & Co Budget
● BLOCKED ON 2 & 4
Kate · Finn
Real budget funding both engines, replacing the flat rollover.
NEXT: Calculate cash needed to fund Sessions 1–4
S6 Tech Stack Review
● PARALLEL · NOT STARTED
Kate + Tristan · Shelby · Jack · Finn
Confirmed tooling decisions and cost/ROI read.
NEXT: Decide who works the 20 unworked Kisaco leads
S7 Roll-Up
● BLOCKED ON ALL ABOVE
Kate + Eddie + Tristan · Finn · Marcus
One integrated Advisory + Ignite view and decision log.
NEXT: Set the next review cadence