## Slide 1
Prepared for: Wendy McHenry, Glenn Wallace
A Conversation of Possibility- Revenue Strategy to Commercial Enablement
All materials and methodologies are copy written and protected Intellectual Property of Kate Burda & Company and for the express purpose for Flying Horse Resort, systems, and constructs are not for external distribution and are protected.

## Slide 2
Insight Intelligence Report
What You Get
So You Can
Understand what:
Is working and needs to be repeated
What is missing and needs to be built
What isn’t working and needs to be left behind
Timeline
Kate & Co
Team
Kate
Sharla
2
1 – The Reveal | Operational Plan
Tristan
A deep dive into:
Critical Crowd Involvement: (Sales Team, Wendy, Glenn, Rev Mgmt., Marketing)
One-on-One Interviews
Rev. Mgmt. & Marketing Calls
Sales Team
Deep dive into:
Revenue Plan
Sales Action Plan
Marketing Plan
Reports, KPIs, and other relevant information
Processes and Involvement:
‘In the tent’
Current strategies, actions
Approach
4 - 5 weeks
Flying Horse Team

## Slide 3: The Reveal- Outline of effort
Week 1:
1 to 2 weeks prior to Kick Off w/ Team
Communication Touchpoint to Team:
Communication sent to the team speaking to:
  Introduction to the project
  What we are expecting to gain
  Introduction of Kate and why she was chosen to partner with Flying Horse
  Next Steps – Kick off Call
  Focus: Access – Information Dump
  Access to Relevant Reporting (Revenue Plan, Sales Strategies, Budgets, KPIs, Marketing Plan, Weekly / Monthly Reports that are submitted, Owners Presentations)
  Schedule of typical meetings- Rev mgmt., Marketing, Sales
  What is being done with KB & Co:
    Deep Dive: Reading, research, understanding, thinking
    Plan Development of the Reveal: Build out of workstreams, milestones, supporting departments and framework and dependencies.
  Flying Horses Resort Team input need:
  Access to the reports and information needed for KB & Co
Virtual
Week 2:
Kick Off w/ Team
Communication Touchpoint to Team:
Warm Invite “Premier” to call
  Focus – Engagement Communication
  Sharing with team of engagement and next steps.
  What is being done with KB & Co:
    Call Design, focused outcomes
February 28

## Slide 4: The Reveal- Outline of effort
Week 2:
(cont.)
  Flying Horses Resort Team input need:
  Availability for individual calls,
  ”In the Tent” - Rev. Mgmt. call, Sales Mtgs, Marketing Mtgs.
Virtual
Week 3:
In the Weeds
Communication Touchpoint w/ Glenn & Wendy – end of visit wrap up
  Focus – Exploration and Understanding
  What is being done with KB & Co:
    Property visit
    Calls, Meetings, Research
  Flying Horses Resort Team time / input needed:
  Availability for individual meetings
  ”In the Tent” - Rev. Mgmt. call, Sales Mtgs, Marketing Mtgs.
  Wendy / Glenn- Wrap up
Onsite- 2 days
March 18

## Slide 5: The Reveal - Outline of effort
Week 5:
In the Lab
Focus- Insight Intelligence Report Build
Putting together the report illustrating the findings, what the steps forward need to be, and the prioritization. This report then frames the Vision-to-Value Roadmap of what is needed to implement.
  What is being done with KB & Co:
    We are heads down putting together the deliverable of the Insight Intelligence Report.
Flying Horses Resort Team:
  Nothing Required- with exception of possible quicks asks for information that we may be missing.
Virtual
Week 4:
Same song 2nd Verse
  Focus – 2nd week continued exploration
  What is being done with KB & Co:
    Property visit
    Calls, Meetings, Research
  Flying Horses Resort Team time / Input needed:
  Availability for individual meetings
  ”In the Tent” - Rev. Mgmt. call, Sales Mtgs, Marketing Mtgs.
Virtual
THIS WEEK – March 24th
Delivered: April 4th

## Slide 6: The Reveal - Outline of effort
Week 6:
In the Weeds
  Focus – Insight Intelligence Report
  Sharing of insights, vetting and prioritizing.
  What is being done with KB & Co:
    Property visit
    Calls, Meetings, Research
  Flying Horses Resort Team time / input needed:
  ½ Day w/ Glenn and Wendy
Onsite
  Communication Touchpoint w/ Team- Thank you
Week of April 7

## Slide 7
Vision-to-Value Roadmap Implementation Plan
What You Get
So You Can
Have a step-wise program that clarifies how we are going to get it done.
Gives you insights to ‘what the best do differently’
Creating the roadmap that builds:
Foundation:
The strategies and goals of the Flying Horse Resort are connected to the larger vision and financial outcomes.
The steps to be taken or initiatives that support the strategies and anticipated outcomes.
Revenue to Commercial Plan
Framework:
Revenue Plan
Needed programs, development, & output
Technology and tools
Resource allocation (capacity)
Focus:
Milestones
Stakeholder Engagement
Advised KPI and Metrics
Timeline
Kate & Co
Team
Kate
Sharla
7
2 – Insight to Execution| Operational Plan
Tristan
3 weeks

## Slide 8: Insight to Execution- Outline of effort
Week 8 :
Presenting the Plan
Focus: Vision-to-Value Roadmap Presentation (implementation plan)
Outlines actions, training, support, through the lens of Foundation (what do we need to put into place in terms of people, approach), Framework (resources and tools), Focus (governance, cadence, accountability) of materials and needed support documentation. Prepare documentation that can guide further implementation steps.
Flying Horses Resort Team:
  2 hours Glenn and Wendy review
Virtual
Week 7 :
Back in the Lab
Focus: Vision-to-Value Roadmap Build (implementation plan)
Outlines actions, training, support, through the lens of Foundation (what do we need to put into place in terms of people, approach), Framework (resources and tools), Focus (governance, cadence, accountability) of materials and needed support documentation. Prepare documentation that can guide further implementation steps.
  What is being done with KB & Co:
    Heads down working, focused and coffee breaks
Flying Horses Resort Team:
  Nothing
Virtual
Delivered: April 18
Review week of April 21

## Slide 9: Investment for Performance
Flying Horse Resort | Revenue Strategy Commercial Enablement
$12,000
Week 1 t Immersion, Dive into reports, performance Virtual
strategies, action plans
Week 2 t Kick Off and Communicated Virtual
Project Plan
Week 3 t Deep dive into approach Market Visit
Week 4 t Continued exploration Virtual
Week 5 t Insight Production Virtual
Week 6 t Insight Intelligence-Presentation 1/2 day
Deliverables: Insight Intelligence Report, Executive Summary, support documents, findings, and recommendations.
The Reveal
Week 7 t Vision-to-Value Roadmap Development- Virtual
Week 8 t Vision-to-Value Presentation Virtual
Week 9 t Buffer
Deliverable: Vision-to-Value Roadmap, Revenue Plan
Insight to Execution
$8,000