ActiveCampaign Training Program

▬▬▬▬▬▬▬

FEI Dallas  |  Four Sessions

Prepared for Kate Burda  |  October 5, 2026

Working plan: what each session covers, who attends, and what we hand out

# How Every Session Runs

One hour, recorded. Nancy (or the person being trained) shares their screen and does every click. Kate talks them through it. No demonstrations.

Three pieces per session. A short intro deck to open, a click-by-click run sheet for Kate, and a leave-behind deck with every step.

Built on the real account. Lists, tags, fields, and automations below come from feidallas.activehosted.com, checked October 5, 2026.

Jay's session runs separately. Same structure, focused on membership.

# Who Attends

| Person | Role | What they need |
| --- | --- | --- |
| Nancy Ehlers | New members and the responses we send them | Hands-on skills in every session. She becomes the daily user. |
| Tristan Carty | Owns marketing with Kate; drives the marketing side of pipeline | Hands-on skills, plus list, tag, and automation upkeep. |
| Jackie Dunn | Executive director (not in the program) | A one-page view of what the system does and what she can see. |
| Jay Smith | Membership (separate session) | Membership pipeline and ambassador tracking. |

# What We Found in the Account

1,440 contacts across 14 lists and 37 tags.

Five users: Jackie Dunn, Sharla Hibberd, Tristan Carty, Ryan Doyle, and Nancy Ehlers.

No pipelines are built yet. The Deals area is open and shows a Create a pipeline prompt, so the CRM may already be included. When Kate builds, check whether it asks for the Pipelines add-on (quoted at $68 a month in the July CRM Scorecard).

The renewal series is switched off. Renewal 1 through 6 and Transfer are all off. New Member Onboarding, Trial, Prospective members, and Attended an Event are on.

Website Contact Form lands people in Other. This is the Jeff McKissack issue. Fix the routing in Session 3.

Tag clutter. Duplicates and one-offs such as Aug and August, May !, Feb 2, and March 30. A cleanup task for Tristan after Session 1.

Lists to retire or hide: Newsletter - DO NOT USE, test listings, and Other once the form is fixed.

# Session 1: Contacts and Contact Management (Today)

Goal: Nancy's members and prospects move out of her Excel file and her Outlook, and into ActiveCampaign, where the whole team can see them.

### What we cover

Why one shared record matters: transparency, continuity, and follow-up that doesn't depend on one person.

Reading a contact record section by section: top of page, About fields, Tags, Lists, Automations, Notes and Emails, and Recent Activities.

Adding a contact by hand: search first, Add a contact, custom fields, then tag, list, and a note on the new record.

Three words: List, Tag, and Field, using FEI's real ones.

Getting a spreadsheet ready: one row per person, email required, colors don't import, Save As CSV.

Nancy imports a 10-row test, checks it, then imports the rest.

Working a record: add a note, change a tag, update a field. (No Tasks section until Pipelines are on.)

Nancy's new daily routine and what to finish before Session 2.

### Pieces

Intro deck (8 slides)

Click-by-click run sheet

Leave-behind deck (16 slides)

# Session 2: Deal Pipeline

Goal: see every prospect and sponsor as a stage, so nobody gets lost between hello and joined.

### Kate prepares

Build two pipelines: Membership and Sponsorship.

Membership stages (suggested): Inquiry, Contacted, Attended an Event, Application Sent. Joined is marked Won; Not Now is marked Lost.

Sponsorship stages (from Ryan Doyle's requirements): Identified, Contacted, Proposal Sent, Negotiating. Signed is marked Won; declined is marked Lost.

Connect Nancy's and Tristan's Outlook, so emails log to the record instead of living only in Outlook.

### What we cover

Why a pipeline: the board can see how many prospects we have and where each one stands.

Create a deal from a contact Nancy imported in Session 1.

Move a deal between stages, and assign the owner.

Add a task and a note on the deal.

Filter the pipeline: what's mine, what's stuck, and what's overdue.

Tristan: how marketing feeds the top of the pipeline (forms, campaigns, and events).

# Session 3: Automations

Goal: the system sends the welcome, the reminder, and the follow-up, so nothing depends on memory.

### Kate prepares

Review the 19 automations. Decide which stay on, which turn back on (the renewal series), and which retire (Automation 15, Invite to Follow).

Fix the Website Contact Form so new people get the right list and tag instead of Other.

Connect Pipelines and automations: for example, a new website inquiry creates a deal at the Inquiry stage and a task for Nancy.

### What we cover

What an automation is, in plain words: when this happens, do that.

Walk through New Member Onboarding step by step, so the team knows what members receive.

Nancy and Tristan read an automation's report: who is in it, and who finished.

Safely add or remove a contact from an automation.

Turn the renewal series back on together, after a content check.

# Session 4: Your Role in the System

Goal: each person leaves with a short, clear list of what they own every week.

| Person | Weekly deliverables (draft for Kate to confirm) |
| --- | --- |
| Nancy | Every new inquiry in ActiveCampaign within one business day. A note on every conversation. Welcome response sent from the record. Follow-up tasks cleared or rescheduled by Friday. |
| Tristan | Campaign calendar and sends. List and tag upkeep (no new one-off tags). Membership and sponsor pipeline review with Kate. Monthly marketing report pulls from ActiveCampaign. |
| Jackie | One-page overview of the system. A monthly snapshot: new members, open prospects, sponsor pipeline, and renewal status. |
| Jay (separate) | Membership pipeline and ambassador assignments, from his CRM requirements. |

# Open Items for Kate

When building pipelines, check whether ActiveCampaign asks for the Pipelines add-on. If it does, confirm FEI approves the cost first.

Ryan Doyle is a user and owns the sponsorship requirements. Decide whether he joins Session 2 or gets his own session like Jay.

Sharla Hibberd is still a user. Confirm whether she stays.

Confirm the draft weekly deliverables above before Session 4.