# FEI Dallas: Strategy to Execution Case Study Fact Base

Client: FEI Dallas (Financial Executives International, Dallas chapter). Professional membership association for senior finance executives. Can be named publicly. Story frame (per Kate, 2026.10.06): strategic planning to execution. How they planned before, the plan we built, how it became execution, what changed. ABM / LinkedIn outreach is one execution piece, not the frame. Story spine (Kate, 2026.10.06): The 2024 work (ActiveCampaign, Sales Navigator, Dripify, board reporting) was the marketing tech stack, not the strategy. The strategy story is Elevate: we set the vision first (the Winning Aspiration and the ELEVATE model: Expected Outcomes, Winning Aspiration, Positioning, Headwinds and Tailwinds, Ideal Member Profile, Where We Play, Core Capabilities, Governance/Cadence/Accountability), then used it as the guide that directs everything after: the 4 initiatives, the 65 committee actions, the Strategic Alignment Report that checks every action for drift against the vision, the supervisory committee that carries it across presidents, and the marketing, outreach and sponsorship work. Sources: CF/Strategic Planning/Strategy Sessions August/Elevate Framework.docx, CF/Strategic Planning/Elevate Planning.docx, CF/Strategic Planning/FEI Dallas Strategic Planning 2025.docx, CF/Strategic Planning/Outputs for Strategic Plan/ (Strategic Alignment Overview, Presidents Board Guidance, Actions by Committee).

Compiled: 2026.10.06, read-only pass over the FEI client folder and the AI Brain. Rule used: a number appears here only if a document states it. Each fact carries its source. “Not found in files” means I looked and it is not there.

Path shorthand: - CF/ = /Users/kate/Library/CloudStorage/OneDrive-KateBurda&Company 2/Kate & Co/Client Files/FEI/ - AIB/ = /Users/kate/Library/CloudStorage/OneDrive-KateBurda&Company 2/My-AI-Brain/My AI Brain/

## 1. Before state: how FEI Dallas planned and grew

### How they planned

- The last formal strategic plan in the files is from 2014-15, done with The Richards Group. Source: CF/Strategic Planning/Richards Group 2014 Strategic Planning/.

- At the August 2025 board meeting, KB&Co’s research summary said playbooks, documented decisions, routine handoffs and quarterly reviews “are missing, impacting continuity”. It also cited over-reliance on key or legacy individuals and onboarding and committee transitions that needed more structure. Source: CF/Board - Sponsors/FEI 2025 Board Meeting V5.pptx (Aug 28, 2025), Continuity & Governance slide.

- Leadership turns over every year. Past president Jim Howe, in his planning interview: committees are turned over “to different people every year”, and “we succeed year after year in spite of ourselves”. Source: CF/Strategic Planning/Ella Inputs/Jim Howe Interview.docx. Internal interview, see Section 6.

- The March 2026 alignment report says that before the plan, the chapter ran “an acquisition strategy with no IMP [Ideal Member Profile] filter and no funnel. Activity is high; conversion data is zero.” Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Elevate Strategic Alignment Overview.docx (March 2026, marked Confidential).

### How they grew membership

- Growth came mainly from word of mouth and member referrals. In the 2021 member survey (a university project, not KB&Co work), members said they were introduced to FEI mostly by word of mouth. Source: CF/FEI Surveys/2021/FEI Dallas Presentation for Board Meeting.pptx.

- The Insight Intelligence Report (Feb 2024) said traditional outreach works: “the conversion ratio of potential member to member campaign eclipses marketing outreach by more than 25%.” Source: CF/Deliverables/FEI Insight Intelligence Report.docx.

- Outreach before KB&Co fell into three or four streams: newsletters (Sharla and National), social posts about new members and events (Frontier Marketing), renewals (PropFuel, with National sending its own renewals too), and member-to-prospect asks. The report found it consistent but “very ‘we’ focused”, with “no sense of community” or personalization in renewals. Source: same report. The V4 edit adds “Nancy been following up on leads”. Source: CF/Pitch and Agreements/FEI Insight Intelligence Report V4.docx.

- Digital marketing before KB&Co was run by Frontier Marketing at $1,087.50/month: 3 posts a week on LinkedIn, Facebook and Instagram, plus LinkedIn ad management ($150) and ad budget ($300). Per KB&Co’s later proposal, there was no outreach strategy, lead generation, CRM, reporting or advisory. Sources: CF/Pitch and Agreements/Digital Marketing Service Proposal REVISED 07.01.25 - FEI Dallas.docx (Frontier’s own proposal), CF/FEI_Digital_Marketing_Proposal.docx (April 2026).

- Before the takeover, LinkedIn ads produced nothing: “Clicks: 0, Leads: 0, Spent: $0”. Source: CF/Marketing Mtg - Board/2025/FEI Marketing Outreach Nov.docx (November 2025).

- Website: “No analytics access, no tracking, no landing page optimization.” Messaging and brand voice were “not centrally managed”. LinkedIn was “managed independently of overall strategy”. Source: CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx, “The Starting Point” slide. The April 2026 proposal adds: “Website redirected to national, no local analytics.” Source: CF/FEI_Digital_Marketing_Proposal.docx.

### How they grew sponsorship

- Sponsorship was relationship-driven, with an “analog” offer. “Sponsors cannot measure what they get from FEI today… only as valuable as the person a sponsor happens to sit next to at a monthly meeting.” Source: CF/FEI Roadmap/FEI_Dallas_Q1_Q2_Roadmap_Board.pptx (June 2026).

- The benefits were seats, banners, a looping slide at dinner and a printed directory listing. Source: CF/2026 Proposals/FEI Sponsor Proposal KB&Co.docx.

### Baseline numbers (stated in documents)

| Fact | Number | Period / date | Source |
| --- | --- | --- | --- |
| Members surveyed (2021 university project) | 459 members, 195 responses (43%) | 2021 | CF/FEI Surveys/2021/FEI Dallas Presentation for Board Meeting.pptx |
| Member demographics | 78% over age 50; 89% had 20+ yrs experience; 37% CFO title; 71% male | 2021 | same |
| Member count used in pitch | 422 FEI members (x 10% referrals = 42 potential members) | Oct 2023 | CF/Strategic Planning/Strategic Planning Pitch and Agreements/FEI v7.pptx, slide 37 |
| DFW organizations | 3,044 organizations in the DFW Metroplex | Oct 2023 | same |
| Target pool | “over 2,000 executives within the Metroplex that work for organizations of 500 employees or more” with CFO, Divisional/Regional, Acting, Deputy, Treasurer or Financial Director titles | Feb 2024 | CF/Deliverables/FEI Insight Intelligence Report.docx |
| Job changers in pool | “100+ have changed jobs within the last six months” | Feb 2024 | same |
| DFW organizations | “over 3,000 organizations” | Feb 2024 | same |
| Attrition | “Last reporting attrition was 59 (period July 2023 to Feb 2024). National Average is 14, non-weighted.” | Jul 2023 to Feb 2024 | CF/Pitch and Agreements/FEI Insight Intelligence Report V4.docx (sensitive, see Section 6) |
| Staff capacity for marketing | Jackie Dunn: “no capacity”. Nancy Ehlers: “approximately six hours a month”. PropFuel: about 5 hrs/month, “mostly gone unused” | Feb 2024 | CF/Deliverables/FEI Insight Intelligence Report.docx (sensitive) |
| PropFuel renewal campaign (pre-KB&Co vendor) | 88 members emailed, 30 renewed (34%), $21,000 at the $700 rate | Jul 2023 to Jun 2024 | CF/Marketing Mtg - Board/Frontier/FEI Dallas Success Report.pdf |
| CFO share of membership | “CFOs have dropped from 60–70% of membership to 26%” | workshop input, 2025-26 | CF/Strategic Planning/Outputs for Strategic Plan/FEI Strategic Plan (Final Compiled).xlsx, Member Experience sheet (sensitive) |
| LinkedIn baseline | 13,999 impressions, 286 clicks, 350 reactions, 682 engagements, 40 followers gained | Nov 2025 (last month before KB&Co took over LinkedIn) | CF/Marketing Mtg - Board/2025/FEIDallasNovemberSocialMediaReport.pptx |
| LinkedIn prior-year impressions | March 13,541; April 24,624; May 19,445 | Mar to May 2025 | CF/Board Retreat.pptx, slide 5 chart |
| LinkedIn prior-year engagement | March 3,219; April 2,818; May 2,113 | Mar to May 2025 | CF/Board Retreat.pptx, slide 6 chart |
| Cash sponsorship | FY25 $617,119; FY26 $642,825 committed (104% of prior year) | as of 9/23/25 | CF/Board - Sponsors/Sponsorship_Sept 2025_WITH DETAIL.pdf (sensitive) |
| Sponsor count | 45 annual sponsors (43 unique), 55 total incl. event sponsors; 35 chapter sponsors | FY26, as of 9/23/25 | same |
| Membership growth goal set in plan | 450 members | target 2029/2030 | see Section 2 |

Current member count: the 2026 sponsor proposal says “a curated community of 300 members” (CF/2026 Proposals/FEI Sponsor Proposal KB&Co.docx). The alignment report says “300 members don’t list FEI on LinkedIn”. No document gives an official member count by date. Roster snapshots exist in CF/Current -Roster/ (Nov 2024 through Apr 2026) and CF/Copy of FELDallas_Roster_260806.xls, but none states a total. Needs Kate or Nancy. Read side by side (459 in 2021, 422 in 2023, about 300 in 2026), these figures point to a decline. Handle with care (Section 6).

## 2. The strategic plan we built (Elevate)

### Phase 0: Diagnosis (late 2023 to early 2024)

- Pitch: “A Conversation of Possibility”, prepared for Miguel Molina, Scott Smaistrla and Alice Elkins. The 5-step “Rapid Revenue Return” covers The Reveal, Insight to Execution, Install/Enhance/Elevate, Drive & Sustain, and Measure & Equip. Files are dated Sept to Oct 2023. Source: CF/Strategic Planning/Strategic Planning Pitch and Agreements/FEI v7.pptx. The executed version is CF/Pitch and Agreements/Marketing Agreements Ongoing/FEI_KBurda_Marketing_Proposal Executed.pdf, dated 2023-11-30.

- Discovery (Jan 2024): interviews with members (May Lee Harris, Tom Beitel, Mark Dendle, Jim Howe, new member Iain Grant, Ron Rushing) and the internal team (Jackie, Nancy, Sharla). Also conversations with PropFuel, National, Frontier and a competitive scan (CFO Leadership Council). Tech finding: National’s robust system was 12-18+ months away, so the advice was a “simplified tech stack” now. Source: CF/Marketing Mtg - Board/2024/FEI Update Jan 18.docx.

- Insight Intelligence Report + Findings & Recommendations (Feb 2024): set the marketing goal (“50 new members annually along with decrease of attrition”). It recommended direct outreach to the 2,000 Metroplex executives by career stage, a shift from “us” to “them” messaging, leaving renewals to National, a CRM (ActiveCampaign), Sales Navigator, Dripify, and SEMRush/GA analytics. It also set roles: Nancy on admin and workflow, volunteers on final-stage outreach, and an advisor role. It said the proposed systems were “net neutral”. Sources: CF/Deliverables/FEI Insight Intelligence Report.docx (2024-02-14), CF/Deliverables/Findings and Recommendations.pptx / .pdf.

### Phase 1: The Elevate strategic plan (June 2025 to March 2026)

- Framework: Roger Martin’s “Playing to Win” cascade (aspiration, where to play, how to win, capabilities, management systems), adapted into KB&Co’s ELEVATE framework. Its parts are North Star, Expected Outcomes, Positioning, Headwinds/Tailwinds, Ideal Member Profile, Where We Play, Core Capabilities, Continuity & Governance, and Winning Aspiration. Sources: CF/Strategic Planning/FEI Playing to Win.docx (June 2025), CF/Strategic Planning/Strategy Sessions August/Elevate Framework.docx.

- Sprint plan: July 11 to mid-August 2025: kickoff, stakeholder interviews, market and competitive scan, draft, a one-day workshop, then a board-ready plan. Sources: CF/Strategic Planning/FEI Roadmap.docx, CF/Strategic Planning/Elevate Planning.docx.

- Method as reported to the board: “15 In-depth interviews with the FEI Board, members, and sponsors”, a “Detailed market scan”, “Two collaborative workshops, real-time synthesis, consensus voting”, and “15+ hours interviews, 40+ hours of research”. Every point reflects a steering committee or board decision: “a ‘by us, for us’ plan”. Source: CF/Board - Sponsors/FEI 2025 Board Meeting V5.pptx (prepared for the Aug 28, 2025 board meeting).

- Engagement agreement for this phase: dated Aug 13, 2025. Length “June 2025 - August 2026”. Signed for FEI by Tom Beitel. Source: CF/Strategic Planning/SOW Strategic Plan/FEI 2025 agreement_kB co.pdf. Assets from the phase included a brand book, monthly meeting videos and a landing page. Source: CF/Strategic Planning/SOW Strategic Plan/Invoicing 2025.xlsx. Video scripts are in CF/Videos/.

- Launch: the plan called for a chapter launch on Sept 8, 2025, presenting the manifesto and first video at the chapter dinner. Source: CF/Board - Sponsors/FEI 2025 Board Meeting V5.pptx, timeline slide. Not confirmed in files that this happened as planned.

### What the plan decided

Source for all of this: CF/Strategic Planning/FEI Decision Points- one pager.pdf (Mar 2026), CF/Strategic Planning/FEI Dallas Strategic Planning 2025.docx, CF/Board - Sponsors/FEI 2025 Board Meeting V5.pptx. - Winning aspiration: “FEI Dallas elevates and connects finance leaders, building a dynamic community where innovation thrives, growth accelerates, and collaboration shapes the future of North Texas.” Tagline: “Your Legacy Belongs Here.” - Positioning: redefine “premier” as innovative, bold and trailblazing, keeping a warm, welcoming core. Board deck data point: 20+ Dallas organizations use similar language. - Competition reframed: the real competitor is the executive’s time. The goal is “Return on Time” and “the most valuable room in Dallas”. - Strategic goals: membership of 450 with an 85% retention rate; a cost-neutral income statement by 2029; recognition as trusted and best in class for forward-thinking leaders. Note: the Nov 2025 planning doc says 95% retention by 2029, while the Mar 2026 one-pager and alignment report say 85% (the alignment report and board guidance say “by 2030”). Confirm with Kate which is final. - Ideal Member Profile: core is $100M to $2B revenue and 500 to 4,000+ employees. Emerging leaders are $25M to $100M and 300 to 1,000+ employees (the Aug 2025 deck says 150 to 500 employees; confirm). - Personas: Visionary Connector (C-level legacy, “builders of bridges”), Strategic Advancer (rising star, next gen), Community Catalyst (trusted community builder). - Four initiatives: (1) Activation & Member Engagement, (2) Member Experience, (3) Operational Efficiency & Strategy, (4) Brand Awareness. - Required capabilities: a single source of truth (project management across all committee work), operating playbooks/SOPs, dedicated resources assigned to Elevate actions, and technology enablement.

### Phase 2: Strategy to initiatives (Sept 2025 to March 2026)

- Second-round SOW (Sept 2025): two streams: (1) build out the strategic plan with the committees, (2) playbooks/SOPs for operations, on a bank-of-hours basis. Source: CF/Strategic Planning/SOW Strategic Plan/SOW 2nd round of the strategic plan.pptx.

- Initiative workshop: “Understand and Expand”, Feb 28, 2026, 8:00 to 12:00, opened and closed by President Miguel Molina and facilitated by Kate, David and Tristan. Pre-work went out the first week of February: a one-pager, a 2-part foundation video, a strategic worksheet and a tutorial video. Sources: CF/Strategic Planning/Initiative Session/Initiative Workshops.xlsx, Strategic Plan- Initiatives workshop share.pptx, FEI- Work Group Lead.docx.

- Teams: 22 board and committee members were assigned to four initiative teams (Brand Awareness 5, Operational Efficiency 5, Member Experience 7, New Members Engagement 5). The work group leads were Sebastian (Peluffo), Mark (Dendle), Christina (Smith) and Elizabeth (Pospick). Source: CF/Strategic Planning/Initiative Session/Strategic Initiative Teams.docx.

- Outputs (March 2026):

  - Strategic Plan, Actions by Committee: 65 prioritized action items across 9 committees (External Relations 21, Membership 17, Sponsorship 9, SIGs 4, Professional Development 4, Arrangements 4, Social Events 3, Program 2, Academic Technology 1). Each has a fiscal year, initiative, supporting actions and sponsor/partner enablement. Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Actions by Committee.docx.

  - Compiled strategic plan workbook with KPIs per initiative. Examples: gross new members per year; % of qualified guests who join in 6 to 12 months; first-year retention; % of events rated 4.5/5 or higher on “value for my time”; member NPS. Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Strategic Plan (Final Compiled).xlsx.

  - Elevate Strategic Alignment Report (board, March 2026): grades each initiative. Activation is “Partially Aligned”, Member Experience “Well Structured, Underway”, Op Efficiency “Foundational, Needs Investment”, Brand Awareness “Execution Gap, Highest Risk”. It gives 12 prioritized board recommendations with owners. Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Elevate Strategic Alignment Overview.docx (Confidential).

  - Elevate Presidents & Board Guidance: a governance and continuity guide covering the supervisory committee, presidential handoff protocol (90 and 30 days out), the Elevate Scorecard as a standing board item, the 4-question “Elevate Test”, an action addition protocol, an annual committee charter review and Elevate onboarding for every new leader. Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Elevate Presidents Board Guidance.docx (Confidential).

  - Decision Points one-pager (the “north star” document). Source: CF/Strategic Planning/FEI Decision Points- one pager.pdf.

  - Brand Manifesto, “Driving Why” (Aug 2026). Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Brand Manifesto - Driving Why.docx.

## 3. How the plan was turned into execution (chronological)

| When | What | Owner / rhythm | Source |
| --- | --- | --- | --- |
| Apr to May 2024 | Digital install: Sales Navigator, Dripify and ActiveCampaign sign-up and onboarding, contacts and forms moved out of PropFuel, FEI Dallas LinkedIn account, training for Nancy | Jawaria (KB&Co), Kate, Nancy, Jackie | CF/Marketing Mtg - Board/2024/FEI Install Roadmap.xlsx; agreement CF/Pitch and Agreements/Marketing Agreements Ongoing/Marketing Agreement.pdf (Apr 2024) |
| Jun to Jul 2024 | Lists and automations built (onboarding, renewal, prospective, attended an event). NetForum-to-ActiveCampaign admin process. “Install Complete” (July 18 huddle) | Jawaria, Kate | CF/Marketing Mtg - Board/2024/FEI June 10.docx, FEI Huddle 7.docx |
| Aug 2024 | Operating rhythm set: Nancy sends member updates to Kate twice a month, Jackie sends sponsor updates monthly. 6-touch renewal series running (60 days prior through 60 days post). Frontier leads, referrals and event attendees flow into AC | Nancy, Jackie, Kate | CF/Marketing Mtg - Board/2024/FEI Huddle 8-16.docx, CF/Marketing Mtg - Board/2025/FEI Architcture - TB.docx |
| Sept 2024 onward | Monthly marketing call and board outreach report | KB&Co | CF/Marketing Mtg - Board/2024/FEI September.pptx, monthly docs in CF/Marketing Mtg - Board/2024 and /2025 |
| Jan to Jun 2025 | Monthly reporting continues (contacts, campaigns, Dripify, “On the Move” job-change list, promotions) | KB&Co | CF/Marketing Mtg - Board/2025/*Reporting*.docx |
| Jun 2025 to Mar 2026 | Elevate strategic plan (Section 2) | KB&Co with board | Section 2 sources |
| Sept 2025 onward | Contract: weekly marketing outreach and LinkedIn outreach retainers, with a monthly progress report | KB&Co | CF/Strategic Planning/SOW Strategic Plan/FEI 2025 agreement_kB co.pdf |
| Oct to Nov 2025 | Digital Marketing Agreement: KB&Co takes over Frontier’s LinkedIn scope (Part 1) and adds email outreach and database work (Part 2). Final version dated Nov 17, 2025 | KB&Co | CF/Pitch and Agreements/Marketing Agreements Ongoing/FEI- Digital Marketing Agreement_Final.pdf |
| Nov 2025 | New LinkedIn cadence: Tue member spotlights, Wed sponsor recognition, Thu event promotion, weekly “FEI Dallas Weighs In” poll | KB&Co | CF/Marketing Mtg - Board/2025/Nov FEI Marketing Outreach.docx |
| Dec 2025 | “LinkedIn takeover begins”. KB&Co “took over the full program in December 2025” | KB&Co | CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx; CF/FEI_Digital_Marketing_Proposal.docx |
| Q1 to Q2 2026 | Weekly Monday prospect email to mid-cap CFOs (“Convince, Curate, Communicate”), with sponsor thought leadership woven in | KB&Co | CF/FEI Dallas Q2 Elevate Sponsorship Engagement Package.docx |
| Feb 2026 | Board marketing partnership review: “Fragmented to Integrated” | Kate | CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx |
| Apr 2026 | LinkedIn Outreach Playbook v2: Sales Navigator filters, Dripify sequences and message templates per persona, plus 5 sponsor target segments | KB&Co | CF/FEI_Dallas_LinkedIn_Outreach_Playbook_v2.docx |
| Apr to May 2026 | Marketing Committee planning sheet for FY2026-27, built on Elevate; proposes the Marketing Committee as “ELEVATE Alignment Authority” | KB&Co with Miguel Molina, Irma Santamaria | CF/FEI_Marketing_Committee_Planning_Sheet_2026_27.docx |
| May to Jun 2026 | New feidallas.org (WordPress): launch comms plan (Pre-Game May 14-29, launch May 31 to June 1). By the June 6 board retreat: “feidallas.org is live” | David Garrard (KB&Co), Pragmatik | CF/FEI Website Launch June 1.docx, CF/FEI Dallas Website Launch Comm Plan.docx, CF/Board Retreat.pptx |
| Jun 15, 2026 | Q1 & Q2 FY2027 Roadmap (Jul 1 to Dec 31, 2026): four workstreams (CRM, Sponsorship, Marketing Outreach, Website & Digital), each with a named client sponsor. Two anchor goals: +35 net new CFO members by June 30, 2027 and +$25K net new annual sponsorship revenue | Miguel Molina (CRM, Outreach, Web), Ryan Doyle (Sponsorship), Terry Beneke (close) | CF/FEI Roadmap/FEI_Dallas_Q1_Q2_Roadmap_Board.pptx, _Internal.docx, _Tracker.xlsx |
| Jul 2026 | CRM decision work: HubSpot vs ActiveCampaign scored against 23 requirements gathered from Ryan Doyle and Jay Smith | KB&Co | CF/FEI_Dallas_CRM_Scorecard_v12.xlsx |
| Jul 2026 | Website checklist (38 tasks) and topical authority maps for SEO content | KB&Co | CF/FEI_Dallas_Website_Checklist.xlsx, CF/Topical Authority Map - *.xlsx |
| Aug 2026 | Sponsorship Stage 1 “Understand” playbook: current-sponsor interviews (Kate) and lapsed-sponsor interviews (Tristan) on a shared 5-question spine; source-of-truth workbook | Kate, Tristan | CF/FEI_Dallas_Sponsorship_Stage1_Playbook.docx, CF/FEI_Sponsorship_Stage1_SourceOfTruth.xlsx |
| Aug to Sept 2026 | Membership Committee lead lists + September meeting outreach plan: committee members’ own prospect lists merged into one tracker, de-duplicated, scored against the IMP, given owners, with ready-to-send peer invitation copy | KB&Co with Membership Committee | CF/Membership File/FEI_Dallas_September_Meeting_Outreach_Plan-2.docx, FEI_Dallas_Membership_Committee_Lead_Lists_Sep_10_26_Update.xlsx |
| Oct 5, 2026 | ActiveCampaign training program (4 recorded one-hour sessions: Contacts, Deal Pipeline, Automations, Roles). The trainee does every click while Kate coaches. Session 1 run 10/05 with Nancy | Kate, Nancy Ehlers, Tristan Carty | AIB/my-work (outputs)/clients/fei-dallas/02 - Deliverables/ and /03 - Working Files/ |

### The execution engine as FEI now describes it

“FIND (Sales Navigator) → ENGAGE (Dripify) → NURTURE (ActiveCampaign) → STAY VISIBLE (website blogs and LinkedIn) → CONVERT (Membership & Sponsorship Committees)”. The doc then flags the open gap: “There’s no formal handoff today from a nurtured contact to a member or sponsorship conversation.” Source: CF/Marketing Mtg - Board/6-FEI Dallas June 26 Marketing Report.pptx. The Oct 2026 AC pipeline training is the response to that gap.

## 4. How the team works differently now

Each item is tagged [in place] (a file shows it running) or [designed / proposed] (built and recommended, adoption not confirmed in files).

- One shared plan and a test for every decision [designed / proposed]. There is a winning aspiration, an IMP, four initiatives, 65 actions with owners by committee, and the 4-question Elevate Test. Sources: Section 2. Whether the board formally adopted the supervisory committee, the Elevate Scorecard and the Marketing Committee “Alignment Authority” charter is not found in files.

- Committees plan against Elevate [in place]. The FY27 committee planning sheet template went to the board for the June 6, 2026 retreat. The Marketing Committee sheet lists every action with an “ELEVATE Alignment” column. Sources: CF/FEI Dallas Board Meeting_4-23-26_Discussion Notes-Handouts copy.pdf, CF/FEI_Marketing_Committee_Planning_Sheet_2026_27.docx.

- Initiative teams and leads [in place as of Feb 2026]. 22 leaders on 4 teams, with work group leads acting as “keepers of the Elevate vision”. Source: CF/Strategic Planning/Initiative Session/.

- Named owners per workstream [in place, June 2026]. Client sponsor plus KB&Co execution plus a closer. Example: Sponsorship is Ryan Doyle as sponsor, KB&Co executing, Terry Beneke closing. Source: CF/FEI Roadmap/FEI_Dallas_Q1_Q2_Roadmap_Internal.docx.

- A monthly measurement rhythm with the board [in place]. Monthly digital marketing report with month-over-month, rolling 3-month benchmark and year-over-year views, including “Honest read” notes when numbers cool. Sources: CF/Marketing Mtg - Board/2026/*, CF/Board Retreat.pptx.

- Weekly outreach cadence that does not depend on volunteers [in place]. Weekly Monday prospect email in ActiveCampaign, a Tue/Wed/Thu LinkedIn cadence with weekly polls, a monthly newsletter (Sharla) and continuous Dripify sequences. Sources: CF/FEI Roadmap/FEI_Dallas_Q1_Q2_Roadmap_Tracker.xlsx (status “In Progress”), CF/Marketing Mtg - Board/2025/Nov FEI Marketing Outreach.docx.

- Membership committee works one list, not thirteen [in place, Sept 2026]. One Lead Tracker with an owner, fit tier and invite status per row, “the only place outreach is recorded”. Members send invitations from their own inbox using provided peer copy. Source: CF/Membership File/ files.

- Member records move out of personal spreadsheets and inboxes into one CRM [in progress, Oct 2026]. Session 1 intro deck: “Today, a member’s story lives in one spreadsheet and one inbox… When roles change, the relationships leave with the person.” Membership and Sponsorship deal pipelines are being built for Session 2. Source: AIB/my-work (outputs)/clients/fei-dallas/02 - Deliverables/2026.10.05 - FEI Dallas - AC Session 1 Intro Deck.pptx, 2026.10.05 - FEI Dallas - AC Training Program Plan.docx.

- Sponsorship moves from relationship renewals to evidence [designed, Stage 1 underway]. Interviews, competitive spend, benchmarking, then a tier redesign with a digital layer and ROI reporting. Source: CF/FEI_Dallas_Sponsorship_Stage1_Playbook.docx. The source-of-truth file shows all 11 interviews “Not started” as of its last save (Aug 10, 2026).

- A website they can measure [in place, early]. The site is live with analytics. The June 6, 2026 retreat deck says: “analytics are installed but the data is still early.” Source: CF/Board Retreat.pptx.

## 5. Measurable results

### 5a. Business outcomes (members, renewals, sponsorship revenue, attendance, pipeline)

| Outcome | Finding | Source |
| --- | --- | --- |
| New members attributable to the program | Not found in files. The Feb 2026 board deck says ROI “was impossible to prove end-to-end” until site analytics existed. The June 2026 retreat deck says “the next reporting cycle connects impression to member for the first time.” | CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx; CF/Board Retreat.pptx |
| Progress on +35 net new CFO members (FY27 goal) | Not found in files. |  |
| Renewals / retention change | Not found in files. As of Oct 5, 2026 the AC renewal series (Renewal 1 to 6 and Transfer) is “switched off”. | AIB/.../03 - Working Files/2026.10.05 - FEI Dallas - AC Training Program Plan.docx |
| Sponsorship revenue attributable to KB&Co | Not found in files. The sponsorship workstream started July 2026 and Stage 1 interviews were not started as of Aug 10, 2026. | CF/FEI_Sponsorship_Stage1_SourceOfTruth.xlsx |
| Sponsorship totals (context only, not attributable) | FY26 cash commitment $642,825 vs FY25 $617,119 (104%) as of 9/23/25. April 2026: annual sponsorship $734,875 ($665,625 cash, $69,250 in kind), event sponsorship $53,500. | CF/Board - Sponsors/Sponsorship_Sept 2025_WITH DETAIL.pdf; CF/FEI Dallas Board Meeting_4-23-26_Discussion Notes-Handouts copy.pdf (sensitive) |
| Progress on +$25K sponsor revenue (FY27 goal) | Not found in files. |  |
| Event attendance | Not found in files. Qualitative only: “There has been a recent uptick in sponsors bringing prospective members to meetings” (Membership report, Apr 23, 2026 board notes). | CF/FEI Dallas Board Meeting_4-23-26_Discussion Notes-Handouts copy.pdf |
| Prospect pipeline size (Dripify / LinkedIn) | 1,807 (Mar 2026), 2,271 (Apr), 2,382 (May), 2,449 (Jun), 2,485 (Jul), 2,637 (Aug 2026) total contacts | Monthly reports in CF/Marketing Mtg - Board/2026/, CF/Marketing Mtg - Board/FEI Dallas July 26 Marketing Report - Updated.pptx, CF/FEI_Dallas_August_26_Marketing_Report.pptx |
| Dripify response, May 2026 | 9 replies (+125% vs prior period), 32 invites accepted (+52.4%), 238 emails sent (+221.6%), 132 profiles viewed | CF/Board Retreat.pptx, slide 7 |
| Membership Committee pipeline | Sept 10, 2026: 339 leads (145 added in September), 103 Tier A core targets, 145 Tier B, 16 Tier C, 75 Tier D. 221 reachable by email, 118 LinkedIn only. Status: 22 invited, 1 replied, 5 RSVP No, 311 not yet contacted | CF/Membership File/FEI_Dallas_Membership_Committee_Lead_Lists_Sep_10_26_Update.xlsx, Read Me |
| September 2026 meeting guests / RSVPs yes | Not found in files. |  |
| CRM footprint | Oct 5, 2026: 1,440 contacts across 14 lists and 37 tags, 5 users. No deal pipelines built yet | AIB/.../2026.10.05 - FEI Dallas - AC Training Program Plan.docx |

### 5b. Email engagement

| Metric | Number | Period | Source |
| --- | --- | --- | --- |
| Weekly newsletter open rate | 58-62% | Sept 2024 | CF/Marketing Mtg - Board/2024/FEI September.pptx |
| Weekly newsletter CTR | 13% | Sept 2024 | same |
| Open rate of “asks” | 43-45% | Sept 2024 | same |
| Renewal series | highest click rate 18% (60 days post expiration); 0% bounce | Sept 2024 | same |
| Weekly newsletter | 2,223 sent, 62.5% open, 7.2% CTR, 4 campaigns, 0% bounces, 0.09% unsubscribes | Dec 2025 | CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx |
| Weekly newsletter | 1,719 sent, 65.5% open, 8.6% CTR, 3 campaigns, 0% bounces, 0.12% unsubscribes | Jan 2026 | same |
| Benchmark claim | “Industry avg Open Rate: 21%, Ours: 62–65% (3× benchmark)”; “Industry avg CTR: 2.5%, Ours: 7–9%” | Dec 2025 to Jan 2026 | same |
| Prospective member emails | 763 per month, 80% open rate, 0 unsubscribes (industry avg 20-40%) | as of Feb 2026 | same |
| Prospect email unique opens | “Are you in the Room Where It Happens”: 87. “Capital & Liquidity”: 92 | Mar 2026 | CF/Marketing Mtg - Board/2026/3- FEIDallas March Mktg Report.pptx |

### 5c. LinkedIn (FEI Dallas company page)

KB&Co took over LinkedIn in December 2025. November 2025 is the last pre-takeover month.

| Month | Impressions | Clicks | Reactions | Comments | Reposts | Followers gained | Total engagement | Source |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nov 2025 | 13,999 (+38.2%) | 286 (-60.88%) | 350 | 42 | 4 | 40 | 682 | CF/Marketing Mtg - Board/2025/FEIDallasNovemberSocialMediaReport.pptx |
| Dec 2025 | 44,569 (+218.39%) | 1,254 (+338.46%) | 387 | 34 (43 on engagement slide) | 9 | 29 | 1,693 (+148.24%) | CF/Marketing Mtg - Board/2025/FEIDallasDecember25MarketingReport.pptx |
| Jan 2026 | 45,715 (+2.6%) | 2,033 (+62.12%) | 464 | 29 | 7 | 79 (+172.41%) | 2,533 (+49.62%) | CF/Marketing Mtg - Board/2026/1- FEIDallas January Mktg Report.pptx |
| Feb 2026 | 75,444 (+65.03%) | 3,771 (+85.49%) | 356 (-23.28%) | 32 | 4 | 63 | 4,163 (+64.35%) | .../2026/2- FEI Dallas Feb Mktg Report.pptx |
| Mar 2026 | 93,288 (+23.65%) | 5,688 (+50.84%) | 759 (+113.20%) | 65 (+103.13%) | 13 (+225%) | 74 | 6,525 (+56.74%) | .../2026/3- FEIDallas March Mktg Report.pptx |
| Apr 2026 | 69,705 (-25.28%) | 2,964 (-47.89%) | 678 | 65 | 5 | 78 | 3,712 (-43.11%) | .../2026/4- FEI Dallas April Mktg Report.pptx |
| May 2026 | 70,530 (+1.18%) | 2,894 | 742 | 81 | 14 | 66 | 3,731 | .../2026/5- FEIDallasMay26MarketingReport.pptx; CF/Board Retreat.pptx |
| Jun 2026 | 238,253 (+237.80%) | 915 (-68.4%) | 440 | 26 | 8 | 42 | 1,389 | CF/Marketing Mtg - Board/6-FEI Dallas June 26 Marketing Report.pptx. Per the Aug report, “a sponsored campaign carried June” |
| Jul 2026 | 56,887 (-76.12%) | 2,046 (+123.61%) | 823 (+87.05%) | 36 (+38.46%) | 9 | 60 (42% more than June) | not consistent in deck | CF/Marketing Mtg - Board/FEI Dallas July 26 Marketing Report - Updated.pptx |
| Aug 2026 | 49,202 (-13.51%) | 1,339 (-34.56%) | 651 | 35 | 4 | 51 | 2,029 (-30.59%) | CF/FEI_Dallas_August_26_Marketing_Report.pptx |

Headline claims as the documents state them: - “+227% vs. baseline” impressions (Jan 2026 vs Nov 2025) and “LinkedIn integration took 2 months to produce +227% impression growth”. “+270% Engagement growth”. CTR “4.4%… 8x the LinkedIn industry average of 0.5%”. Source: CF/Marketing Mtg - Board/2026/Board Meeting Marketing Feb 26 .pptx. Spot check: 45,715 / 13,999 = +227%; 2,533 / 682 = +271%. Both hold. - “70,530 Impressions, May 2026, +262.7% year over year”; engagement “+76.6% year over year”; CTR 4.2%, “8x the LinkedIn average”. Source: CF/Board Retreat.pptx (June 6, 2026). Spot check vs the slide’s own prior-year May figure: 70,530 / 19,445 = +262.7%. Holds. - “93,288 LinkedIn Impressions, +104% since Dec”; “5,688 Clicks (March), +354% since Dec”; “759 Reactions, +96% since Dec”. Source: CF/FEI_Digital_Marketing_Proposal.docx (Apr 2026). Spot check: clicks and reactions hold, but 93,288 / 44,569 is +109%, not +104%. Use +109% or drop it. - July 2026 (the inventory row): 56,887 impressions, 2,046 clicks, clicks +123.61% MoM, 60 followers (42% more than June). Source as above. Note that July impressions were -76.12% MoM, coming off the sponsored June.

### 5d. Website, SEO and AI visibility (post-launch, early)

| Metric | Number | Period | Source |
| --- | --- | --- | --- |
| Site launched | feidallas.org live on new WordPress platform | by June 6, 2026 | CF/Board Retreat.pptx |
| Website checklist | 38 tasks, 5 complete | July 2026 | CF/Marketing Mtg - Board/6-FEI Dallas June 26 Marketing Report.pptx |
| On-page | Alt text 198/200, title tags 10/89, schema 1/79 | July 2026 | same |
| Technical SEO | OTTO installed, 365/365 pages healthy, technical score 90/100; Authority 3/100, Content 6/100 | verified 8/20/26 | CF/Marketing Mtg - Board/FEI Dallas July 26 Marketing Report - Updated.pptx |
| Digital PR | “DFW Finance Leaders Address CFO Challenges and 2026 Forecasts”, published 8/13/26 | Aug 2026 | same |
| Content | Content score 31/100 (up 25 points); 15 executive articles drafted (quality 76 to 96), publish status being confirmed | Aug 2026 | CF/FEI_Dallas_August_26_Marketing_Report.pptx |
| Technical | 438 pages tracked, score 91/100; 720 automated fixes staged, not yet deployed | Aug 2026 | same |
| AI search visibility | Score 65.6, up 11.4% from 58.9 in July; 3,688 citations across AI assistants (+53.3%); ChatGPT referred 10 sessions at 80% engagement | Aug 2026 | same |

### 5e. Strategy-phase outputs (countable)

- 15 in-depth interviews; 15+ hours of interviews and 40+ hours of research; 2 collaborative workshops. Source: CF/Board - Sponsors/FEI 2025 Board Meeting V5.pptx.

- 22 leaders on 4 initiative teams at the Feb 28, 2026 workshop. Source: CF/Strategic Planning/Initiative Session/Strategic Initiative Teams.docx.

- 65 prioritized actions across 9 committees. Source: CF/Strategic Planning/Outputs for Strategic Plan/FEI Actions by Committee.docx.

- 12 prioritized board recommendations with owners. Source: FEI Elevate Strategic Alignment Overview.docx.

## 6. Usable client quotes

No clean, attributed, approved client testimonial about KB&Co’s work was found. The transcripts are auto-generated, mostly unlabeled (“Speaker 1”), and recorded as internal planning conversations. Every quote below needs Kate to confirm the speaker and get permission before it goes public.

| Quote (verbatim) | Speaker | Use | Source |
| --- | --- | --- | --- |
| “But no, I love it. We just need to find folks to help us, you know, institutionalize this now.” | Unlabeled. The next line (“And Jackie? Everything Jay said.”) suggests Jay Smith. Confirm. | Reaction to the 2025 plan pitch | CF/Pitch and Agreements/2025 Pitch/Transcript FEI.docx |
| “very, very, very few of them know who we are, so we’re not reaching… the core people that qualify for membership” | “Speaker 1”, an FEI member/leader with an M&A network. Name unknown | Before state (brand awareness) | CF/FEI Brand Awareness Conversation.docx (Apr 2026) |
| “I was fell down standing up when I heard what Kate made in initial progress.” | same “Speaker 1” | Garbled transcription of praise. Do not use verbatim. Ask the speaker for a clean line | same |
| “we succeed year after year in spite of ourselves” | Jim Howe, Past President | Before state (planning and continuity). Confidential interview, needs permission | CF/Strategic Planning/Ella Inputs/Jim Howe Interview.docx |
| “I posted about it and I tagged [FEI] Dallas and I got over a thousand impressions on it.” | “Speaker 6”, a member in the recruitment workshop. Name unknown | Illustrates the member LinkedIn activation idea | CF/Strategic Planning/Supporting Doc and Transcripts/Member Recruitment and Engagement Strategies-transcript.docx |

Recommendation for Kate: ask Miguel Molina (President during Elevate) or Mark Dendle (incoming President) for a 2-3 sentence approved quote on the plan and the shift to execution.

## 7. Sensitive: keep out of the public case study

- Fees and pricing: $10,000 / $10,540 initial engagement, the $2,000 + $360 monthly retainers, the $2,787 retainer, the proposed $2,900 / $3,500 / $4,000 rates, the $16,956 “annual savings” claim, the invoicing totals, the Frontier price comparison and the HubSpot/AC cost scenarios. Sources: agreements in CF/Pitch and Agreements/, CF/Strategic Planning/SOW Strategic Plan/, CF/FEI_Digital_Marketing_Proposal.docx, CF/FEI_Skills_Competencies.docx, CF/FEI_Dallas_CRM_Scorecard_v12.xlsx.

- Sponsorship financials and named sponsors: dollar totals, per-sponsor pricing and discounts, the “benefits not received” markup, and especially lapsed sponsor names (Moss Adams, Aston Carter, Capital One, ValuLink, UNT; Grant Thornton, Eliassen Group, Workday). Sources: CF/Board - Sponsors/, CF/FEI_Dallas_Sponsorship_Stage1_Playbook.docx, CF/FEI_Sponsorship_Stage1_SourceOfTruth.xlsx.

- Membership decline and attrition: 459 (2021) to 422 (2023) to about 300 (2026); attrition of 59 vs national average of 14; CFOs down to 26% of membership; “300 members don’t list FEI on LinkedIn”. Fine as anonymized “before” color only with Kate’s and FEI’s OK.

- Staff and people matters: capacity assessments of Jackie Dunn and Nancy Ehlers, Jackie’s transition and replacement, and the “incoming Executive Director” commentary. Sources: CF/Deliverables/FEI Insight Intelligence Report.docx, CF/FEI_Skills_Competencies.docx, CF/FEI_Digital_Marketing_Proposal.docx.

- Board dynamics: “drift”, “loudest voice”, “leading through resistance”, and initiatives graded “Execution Gap, Highest Risk”. The alignment report and the Presidents & Board Guidance are both marked Confidential, Internal Use Only.

- Personal data: prospect names, emails, phones and LinkedIn URLs in the lead lists, Dripify exports, rosters, severance and reinstatement reports, and new-member lists. Never publish.

- Board meeting notes include a Zoom link with an embedded password. Source: CF/FEI Dallas Board Meeting_4-23-26_Discussion Notes-Handouts copy.pdf.

- Admin vendor analysis (Brian Steward admin services cost reports). Source: CF/Brian Steward Admin Analysis/.

- Vendor comparisons that read as knocking Frontier Marketing or PropFuel.

- IP: KB&Co materials carry “not for external distribution” notices. The ELEVATE framework can be described, but don’t publish the client’s worksheets.

- Usage right: the agreements state “The Client grants to Kate Burda & Co the right to use the statistical results of any sales campaign or activities planned and executed during the term of this agreement”. This supports using the engagement metrics. Naming FEI publicly is confirmed by the caller; still confirm FEI is fine with the specific numbers.

## 8. Data inconsistencies to fix before publishing

- Retention target: 95% (FEI Dallas Strategic Planning 2025.docx, Nov 2025) vs 85% (Decision Points one-pager, Alignment report, Presidents guidance). The year is 2029 in some files and 2030 in others.

- Emerging leader employee band: 300 to 1,000+ (one-pager) vs 150 to 500 (Aug 2025 board deck).

- “+104% since Dec” impressions claim in the April 2026 proposal should be +109% (93,288 vs 44,569).

- May 2026 report engagement slide repeats April’s figures (Likes 678, Comments 65, Shares 5, Clicks 2,964), while its overview slide says 742 reactions, 81 comments, 14 reposts, 2,894 clicks. The tracker also flags a “Clicks discrepancy (2,894 vs 2,964)”.

- July 2026 report: the first file version is titled “June2026”. Reactions show 823 on the overview and “Likes: 832” on the engagement slide. Total engagement reads “1389110%” and “2923110%” (formatting errors). Use the “Updated” file.

- December 2025 comments: 34 on the overview vs 43 on the engagement slide.

- President’s name: “Miguel Delgado, Outgoing President” in the April 2026 proposal vs “Miguel Molina, President” everywhere else.

- Contact counts: “~1,500” (CRM scorecard, Jul 2026) vs 1,440 (AC account, Oct 5, 2026) vs “2,000+ contacts in active pipeline” (the Dripify/LinkedIn pipeline, not the CRM). Keep them separate.

- “11.4% growth, since we started tracking” (Sept 2024 monthly call notes) does not say what grew. Do not use it without Kate’s context.

## 9. Gaps that need Kate

- Business outcome: how many new members (and CFO members) joined since outreach started, and since July 1, 2026 against the +35 goal? Who can pull it: Nancy or Jay Smith.

- Official member counts at engagement start (late 2023), plan launch (Sept 2025) and now.

- Retention / renewals since the plan, and why the AC renewal series is off.

- Sponsorship: any net-new or upgraded sponsors since July 2026 against the +$25K goal. Status of Stage 1 interviews and the Sept 30 Sponsor Intelligence Report.

- September 14, 2026 meeting: how many invited prospects attended and how many joined.

- Board adoption: did the board formally adopt the supervisory committee, the Elevate Scorecard and the Marketing Committee Alignment Authority? Did the Sept 8, 2025 chapter launch happen as planned?

- Attribution now that the site is live: any GA4 conversion data (membership inquiries) since June 2026.

- An approved, attributed client quote (Section 6).

- Which numbers FEI is comfortable publishing (Section 7).