# Compass Reconciliation, week of 10/5 (catch-up #2)

Janice, Tuesday 2026.10.06, 9:15 AM Mountain. This run started late Monday night and finished this morning. This morning’s report (10/5, 8:02 AM) still stands. This one covers only what changed after it: Update #11 to the Master Schedule, today’s 3B-ii work, and the calendar placements made yesterday afternoon.

All times Mountain. You’re in Colorado through Thursday, Dallas Friday.

The Compass file: last saved Mon 10/5 at 5:15 PM Mountain. I wrote at 9:16 AM today and checked the save time before and after. Only my write changed it. If you have the page open from last night, reload it before you edit.

## What does not foot

The calendar hasn’t picked up Update #11 yet. The Compass has the new order. The calendar still has the old one: - Wed 10/7, 7:30 PM: still “Touch 2 Market Expansion.” Should be Build Revenue Intelligence. - Thu 10/8, 10:00 AM: still “Touch 1 Site Visit Targeting.” Should be Touch 3 Business Transformation. - Fri 10/9: no Touch 1 Revenue Intelligence (11:05 to 12:30) and no Build Market Expansion (1:30 to 3:00). Hotel Evolution sits at 12:30 to 1:30 between them, which fits. - The full change list is in the Master Schedule, Update #11. About 5 minutes for this week.

Two Compass lines are on a different day than the calendar: - LinkedIn “Right, or lucky?” post: Compass says Mon. Calendar has it today, 11:30 to 12:15. - CHM Warnick / MPEA Deck: Compass says Tue. Calendar has it Wed, 5:30 to 5:45 PM. - I left both lines as they are. Tell me which is right.

The LinkedIn post’s trigger is stale. Its flagged-priorities entry fires on “Sales Intelligence switch-on day, target 10/8.” Sales Intelligence switched on 9/30. The page check (right-or-just-lucky live?) is still unconfirmed.

The “LOCKED NUMBERS” line in 10/5 is now wrong in three places. It says BT switches on 10/6 and SI on 10/8 (both are live, 10/1 and 9/30), and that the build-out finishes 12/23 (now Thu 11/19, 54 sessions). Still untouched, waiting on your OK from this morning’s question 3.

The reminders script is stale. weekly_compass_reminders_20261005.applescript was made at 5:32 PM yesterday, before the Compass changed. It still has the old Mon, Tue and Wed sessions. Regenerate it before you run it.

Hours: - businessDevelopment, 10/5: 12.0 hrs target, 12.0 hrs of tasks. It was 11.25 and footed. I added the 45-minute suppression list line and recomputed. - No other category has a target.

Source docs agree. The Master Schedule .md and .docx both carry Update #11 (54 sessions, finish 11/19, both saved 10/5 at 5:16 PM). Jack’s 10/5 build order doc matches them.

Duplicates in delivery, 10/5: Flying Horse has “Automation -3 hubspot” twice. FEI has a blank task. Left for you.

## Day by day against the calendar (rest of this week)

- Tue 10/6 (today): about 15 minutes over. LinkedIn post 11:30 to 12:15 runs into ActiveCampaign with Tristan at 12:00. That ActiveCampaign call isn’t in the Compass. Carina Hunter’s Kisaco note was due to go at 7:00 AM; if you scheduled it from Zoho, it’s out.

- Wed 10/7: fits. Ellis Fordham’s note at 7:00 AM. You’re skipping the Lodge meeting (still on the calendar) for the Wylie review.

- Thu 10/8: Ignite with Tristan (1:00 to 2:00) still sits on the airport block (1:00 to 2:00). Third time flagged.

- Fri 10/9 (Dallas): Ignite (9:30 to 10:00) still sits inside the Advancement Board (8:00 to 10:30). Third time flagged. After that: test booking 10:45, Touch 1 RI 11:05, Hotel Evolution 12:30, Build ME 1:30, strength 5:30. Full but it fits.

- The suppression list (45 min) has no day. Friday after 3:00 or the weekend are the open spots. It’s due Monday.

## What I captured into the Compass (week of 10/5)

- businessStrategy, Kisaco leads: marked settled (Jack works them, you decide and send). Added three subtasks: send Carina Tue (15 min), send Ellis Wed (15 min), yes or no on Jack’s B and C close-out Thu (10 min).

- businessStrategy, founding-partner pricing: marked decided. $20,000 beta, Charter Rate 20% off GA list for three years, “members” not “partners.”

- businessDevelopment, Zoho: Ignite Beta Hold suppression list, 45 min, no day, due Mon 10/12. hoursTarget 11.25 to 12.0.

Nothing else was changed. I didn’t remove anything.

Not built yet: week of 10/12. This morning’s list for it is superseded. From Update #11: - Mon 10/12: Touch 1 Market Expansion 9:30 to 11:00, Wylie call 11:00, Touch 2 Revenue Intelligence plus the RI switch-on checklist 11:30 to 1:00. Suppression list must be done by now. - Tue 10/13: Touch 2 Market Expansion 10:00 to 11:30 (Hyatt meeting). Revenue Intelligence earliest switch-on, your go on the day. Upgrade Zoho Bookings to Basic. Carina follow-up (Jack drafts). - Wed 10/14: Touch 4 BT 11:30 to 1:00, Touch 4 SI 1:00 to 2:30. Ellis follow-up. - Thu 10/15: Touch 3 RI 10:00 to 11:30, Touch 3 ME 11:30 to 1:00. BT and SI Touch 3 send. - Fri 10/16: Build Sales Transformation 10:00 to 11:30. - That’s 8 sessions, 12 hrs of businessDevelopment, before anything else.

## Needs a revisit date from you

Parked in the Session Handoff log, new entry dated 2026.10.06 (items 18 to 24): - Lawyer for the pilot agreement (you pushed it to later) - Erica Lipscomb, PM Hotel Group (on hold) - Beta kit video claims check, and the beta-customer deck (no owner or date) - Dual-purpose accounts: pay both, or a bundle? - GA list price (Session 4)

Still open from this morning: items 3 to 17 in the 10/5 entry.

## Needs your decision

- Suppression list: which day before Monday?

- LinkedIn post and CHM Deck: Compass day or calendar day?

- OK to rewrite the “LOCKED NUMBERS” line to Update #11 (BT live 10/1, SI live 9/30, finish 11/19)?

- Thu and Fri overlaps: still open from last week.

- ActiveCampaign with Tristan today: add it to the Compass under FEI?

## Lane notes

- Megan (workouts): the 10/5 workouts category is still the stub. Her real sessions are on the calendar. Hers to fix; I didn’t touch it.

- Marcus (does it belong): everything I added traces to Session 3B-ii or Update #11.

- Wendy (categories): admin is still empty, now including Zoho Bookings next week.

## Housekeeping

- Nothing written to the calendar.

- This run started Mon 10/5 at 11:47 PM Central and finished Tue 10/6 at 9:16 AM Mountain, not Sun 8:15 PM. Two late runs in a row; worth a look at the schedule.