## Slide 1
Advisory & Ignite — Session Status As of 2026.09.23. One page, printable. Full detail lives in the master plan and each session’s Outputs file.
Done
In progress
Not started
S1
→
S2
→
S3A
→
S3B-i
→
S3B-ii
→
S4
→
S5
→
S6
→
S7
S1 Advisory Strategy
● DONE (8/31)
Kate · Jack · Scout · Finn
3 clients × $25K = $75K new. $460.8K total Advisory revenue, EOY 2027.
NEXT: Nothing. Handed to Janice for the Weekly Compass 9/23
S2 Advisory Pro Forma
● DONE (9/13)
Kate · Finn · Shelby
Pro forma rebuilt: $468.6K revenue, $254.3K after-tax profit.
NEXT: Swap real close dates for the May/Aug/Nov placeholders
S3A Ignite Strategy
● OUTPUT DONE (9/20) · WAITING ON EDDIE
Kate + Eddie, Tristan · Scout · Finn
5 partners. $23.5K 6-mo cash need, $4.7K/partner. Cap table corrected.
NEXT: Eddie signs the equity amendment (reminder 9/25)
S3B-i GTM: Marketing
● DONE (8/31)
Marcus · Kate · Scout · Maxell
Positioning locked (“Revenue Growth System”). Pitch drafted & split.
NEXT: Decide the founding-partner post-beta pricing advantage
S3B-ii GTM: Sales
● NOT STARTED
Jack · Kate · Marcus · Finn
Target list built: Noble, Raines, Crescent, PM Hotel Group. Outreach on hold.
NEXT: Draft the pilot agreement — lawyer not yet named
S4 Ignite Financial Model
● NOT STARTED · OPENS WHEN EDDIE SIGNS
Kate + Eddie, Tristan · Finn · Shelby
Funded model on 3A’s numbers, replacing 2024 assumptions.
NEXT: Load 3A’s numbers into the Ignite financial model
S5 Kate & Co Budget
● BLOCKED ON 4 (2 IS DONE)
Kate · Finn
Real budget funding both engines, replacing the flat rollover.
NEXT: Calculate cash needed to fund Sessions 1–4
S6 Tech Stack Review
● PARALLEL · NOT STARTED
Kate + Tristan · Shelby · Jack · Finn
Confirmed tooling decisions and cost/ROI read.
NEXT: Decide who works the 20 unworked Kisaco leads
S7 Roll-Up
● BLOCKED ON ALL ABOVE
Kate + Eddie + Tristan · Finn · Marcus
One integrated Advisory + Ignite view and decision log.
NEXT: Set the next review cadence

## Slide 2
How the sessions connect
Each arrow is one session’s output becoming the next session’s input. As of 2026.09.23.
Done
In progress / waiting
Not started
OPERATIONS
ADVISORY
IGNITE STRATEGY & MODEL
IGNITE GO-TO-MARKET
S1 Advisory Strategy
● DONE 8/31
3 clients × $25K, EOY 2027
S2 Advisory Pro Forma
● DONE 9/13
$468.6K revenue, $254.3K profit
S3A Ignite Strategy
● WAITING ON EDDIE
5 partners, $23.5K cash need
S4 Ignite Financial Model
● OPENS WHEN EDDIE SIGNS
Load 3A’s numbers
S3B-i GTM: Marketing
● DONE 8/31
“Revenue Growth System” locked
S3B-ii GTM: Sales
● NOT STARTED
Target list built, outreach on hold
S6 Tech Stack Review
● PARALLEL, NOT BLOCKING
ZoomInfo, Zoho, Ignite tools
S5 Kate & Co Budget
● WAITING ON S4
The merge point: funds both engines
S7 Roll-Up
● WAITING ON ALL ABOVE
One integrated view + decision log
Outreach begins
held until S3B-ii is in place
growth thesis
targets
numbers
partners, cash need
positioning, pricing
funded Advisory revenue
Ignite cash need
funded budget
tooling decisions, cost/ROI

## Slide 3
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 1 of 9
S1 Advisory Strategy
● DONE · 8/31
Kate · Jack (pipeline fit) · Scout (ICP research) · Finn (revenue targets)
TOPICS
1. Growth thesis: what “next level” means for Thoughtware, in dollars and clients
2. Target client profile and a realistic timeline
3. Pricing discipline check against the $15K floor
INPUTS None. This is where the plan starts.
OUTPUT 3 dual-purpose clients (Advisory + candidate Ignite partner) × $25K = $75K new revenue. Total Advisory $460,800 by end of 2027. Thoughtware time capped at these 3; extra time goes to Ignite.
FEEDS S2 (revenue assumptions) · S3A (dual-purpose targeting) · S3B-ii (same target list)
ACTIONS 4 of 4 done
☑ Set the growth target: 3 × $25,000
☑ Confirm timeline: end of 2027
☑ Check price against the $15K floor: passes
☑ Hand decisions to Janice for the Weekly Compass (9/23)

## Slide 4
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 2 of 9
S2 Advisory Pro Forma
● DONE · 9/13
Kate · Finn (numbers) · Shelby (built the model)
TOPICS
1. Turn S1’s thesis into monthly revenue assumptions
2. Rebuild 2027_Advisory_Proforma_1.xlsx to model growth, not flat expenses
3. Sanity-check against the IRS ($24,835) and SBA loan payoff
INPUTS S1’s growth thesis: 3 × $25K, one-time fees, EOY 2027.
OUTPUT Formula-driven pro forma. $468,600 revenue ($393,600 recurring + $75,000 new). $254,320 after-tax profit. Fixed a mixed tax rate (now 15%) and stale hardcoded totals along the way.
FEEDS S5 (Kate & Co budget)
ACTIONS 3 of 4 done
☑ Convert S1’s thesis into monthly revenue
☑ Rebuild the pro forma to model growth
☑ Cross-check IRS and SBA payoff: Q1 2027 plan holds
☐ Swap real close dates in for the May/Aug/Nov placeholders

## Slide 5
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 3 of 9
S3A Ignite Strategy
● OUTPUT DONE 9/20 · WAITING ON EDDIE
Kate · Finn (beta economics) · Scout · Jack · Maxell · Marcus · Janice
TOPICS
1. Where Ignite stands: beta slots vs. capacity, beta-to-GA path
2. Realistic near-term revenue, replacing the 2024 assumptions
3. What Eddie, Recardo and Tristan need to hit that path
INPUTS Finn’s 3–5 partner analysis (8/26) · capacity flag from the Launch Timeline.
OUTPUT 5 beta partners. $23,500 six-month cash need, $4,700 per partner. Cap table matched to signed agreements (Kate 70, Eddie 15, Recardo 5, Tristan 2, 8% pool). Draft amendment for Recardo 5%→10%.
FEEDS S4 (financial model) · both 3B tracks, now anchored at 5 partners
ACTIONS 3 of 8 done
☑ Confirm partner count: 5
☑ Build the beta cash-need model
☑ Correct the cap table
☐ Eddie signs the equity amendment (reminder 9/25)
☐ Eddie’s dev/infrastructure costs (5 lines still $0)
☐ Real travel itinerary: Atlanta, Boston, New Orleans
☐ Legal quote once a lawyer is named
☐ Decide onboarding: all partners at once, or staged

## Slide 6
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 4 of 9
S3B-i GTM: Marketing
● DONE · 8/31 · 3 FOLLOW-UPS OPEN
Marcus (ran positioning) · Kate (every decision) · Scout · Maxell (drafting)
TOPICS
1. Fuse framing: roadmap item vs. narrowed pitch vs. hold
2. Full positioning: alternatives, attributes, value, market, category
3. Proof assets: 16:1 ROAS case, HRI hours finding
4. Pitch one-pager, split into external and internal files
INPUTS S1’s dual-purpose targeting · existing brand assets, verified.
OUTPUT Positioning locked: category “Revenue Growth System,” statement, buyer map. Prospect-safe one-pager plus internal source notes. Ignite brand standards captured.
FEEDS S3B-ii inherits this positioning and pricing for outreach
ACTIONS 4 of 7 done
☑ Lock positioning: category, statement, buyer map
☑ Source and verify proof stories
☑ Draft and split the one-pager
☑ Capture Ignite brand standards
☐ Confirm Conductor AI / Revvie / Ella vs. Iggy naming, with Eddie
☐ igniteyourgrowth.com launch check (Tristan, Shelby)
☐ Decide the founding-partner post-beta pricing advantage

## Slide 7
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 5 of 9
S3B-ii GTM: Sales
● NOT STARTED · OUTREACH ON HOLD
Jack (pipeline, outreach) · Kate · Marcus (agreement) · Finn (metrics) · Eddie & Tristan (security)
TOPICS
1. Finalize and prioritize the outreach list
2. Pilot agreement terms: Fuse refund, data ownership, term, exit
3. Data-security and compliance posture
4. Per-partner success metrics, set before day one
5. Get Zoho in active use, incl. 20 unworked Kisaco leads
INPUTS Positioning and pricing from S3B-i · S1’s target profile.
OUTPUT A ready-to-run outreach plan: prioritized list, pilot terms (pending legal review), security posture, success metrics, active CRM.
FEEDS Actual outreach (Launch Timeline Phase 3), held until this closes
ACTIONS 1 of 7 done
☑ Target list: Noble, Raines, Crescent, PM Hotel Group + backups
☐ Draft pilot agreement: Marcus frames, lawyer reviews (none named)
☐ Security/compliance posture (Eddie, Tristan)
☐ Per-partner success metrics (Finn)
☐ Work the 20 Kisaco leads in Zoho (Jack)
☐ Pick who takes a Flying Horse reference call
☐ Hold all outreach until the above are done

## Slide 8
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 6 of 9
S4 Ignite Financial Model
● NOT STARTED · OPENS WHEN EDDIE SIGNS
Kate + Eddie, Tristan (cost inputs) · Finn · Shelby
TOPICS
1. Replace the model’s 2024 assumptions with S3A’s numbers
2. Fix the cap table
3. Reconcile COGS and salaries against the current team
INPUTS S3A’s partner count, pricing and cash need (landed 9/20).
OUTPUT A funded, current Ignite financial model with a correct cap table.
FEEDS S5 (Ignite’s real cash need) · the written basis for the $1.3M–$2M pitch figure
ACTIONS 0 of 4 done
☐ Load S3A’s numbers into Ignite Financial Architecture vkb.xlsx
☐ Confirm Garrard and Tavares are out of the cap table (S3A corrected it)
☐ Reconcile COGS and salaries against the current team
☐ Write down the basis for the $1.3M–$2M figure

## Slide 9
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 7 of 9
S5 Kate & Co Budget
● WAITING ON S4 · S2 IS DONE
Kate · Finn
TOPICS
1. Cash needed to fund the Advisory and Ignite plans
2. Draw vs. reinvestment
3. Debt payoff sequencing
INPUTS S2’s pro forma (done: $254,320 after-tax) · S4’s Ignite model (not built yet).
OUTPUT A real Kate & Co budget that funds both engines, replacing the flat expense rollover.
FEEDS S7 (roll-up)
ACTIONS 0 of 4 done
☐ Calculate cash needed to fund Sessions 1–4
☐ Decide draw vs. reinvestment
☐ Sequence debt payoff
☐ Remove the canceled $199/mo ActiveCampaign line

## Slide 10
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 8 of 9
S6 Tech Stack Review
● NOT STARTED · CAN RUN ANY TIME
Kate + Tristan · Shelby (tool fit) · Jack (daily user) · Finn (cost/ROI)
TOPICS
1. ZoomInfo ($833/mo) against the S1 pipeline plan
2. Zoho as system of record: who works the Kisaco leads
3. Ignite tooling (Vercel, Supabase) against S3/S4 needs
INPUTS S1’s pipeline plan · S3/S4 tooling needs.
OUTPUT Confirmed tech stack decisions and a cost/ROI read.
FEEDS S7 (roll-up). Runs alongside S4 and S5, doesn’t block them.
ACTIONS 0 of 3 done
☐ Evaluate ZoomInfo ROI
☐ Decide who works the 20 Kisaco leads (same item as S3B-ii)
☐ Check Vercel and Supabase against S3/S4 needs

## Slide 11
S1
S2
S3A
S3B-i
S3B-ii
S4
S5
S6
S7
Session 9 of 9
S7 Roll-Up
● WAITING ON ALL ABOVE
Kate + Eddie + Tristan · Finn · Marcus (synthesis)
TOPICS
1. One view: Advisory (cash) + Ignite (growth/equity) under Kate & Co
2. Every open decision from S1–S6 has a Weekly Compass entry
3. Set the next review cadence
INPUTS Every session’s output.
OUTPUT One integrated view and a decision log.
FEEDS Ongoing operation. This is the end of the chain.
ACTIONS 0 of 3 done
☐ Build the consolidated Advisory + Ignite view
☐ Check every S1–S6 decision is on the Weekly Compass
☐ Set the next review cadence